## Report
WEEKLY REPORT
WEEK: 10
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 2016-05-12 | 2016-05-12 | HaiTran | 2 | 2
2 | Review Vision of the soulution | 2016-05-12 | 2016-05-12 |  | 3 | 2
3 | Review prototype for website | 2016-06-12 | 2016-06-12 |  | 6 | 6
4 | Training Technical | 2016-06-12 | 2016-06-12 |  | 2 | 2
5 | Customer Meeting | 2016-07-12 | 2016-07-12 |  | 2 | 3
6 | Write Usecase description "Manage News" Function | 2016-07-12 | 2016-08-12 |  | 8 | 10
7 | Write Usecase description "Manage Categories" Function | 2016-07-12 | 2016-08-12 |  | 5 | 5
8 | Draw Usecase Diagram "Manage News" Function | 2016-08-12 | 2016-09-12 |  | 4 | 4
9 | Draw Usecase Diagram "Manage Languages" Function | 2016-08-12 | 2016-09-12 |  | 1 | 1
10 | Team Meeting | 2016-05-12 | 2016-05-12 | HienNguyen | 2 | 2
11 | Review Vision of the soulution | 2016-05-12 | 2016-05-12 |  | 2 | 2
12 | Review Proposed System | 2016-06-12 | 2016-06-12 |  | 4 | 6
13 | Review Context Diagram | 2016-06-12 | 2016-06-12 |  | 5 | 5
14 | Training Technical | 2016-06-12 | 2016-06-12 |  | 2 | 2
15 | Customer Meeting | 2016-07-12 | 2016-07-12 |  | 2 | 3
16 | Write Usecase description "Manage Accounts" Function | 2016-07-12 | 2016-08-12 |  | 7 | 8
17 | Draw Usecase Diagram "Manage Accouts" Function | 2016-08-12 | 2016-09-12 |  | 5 | 5
18 | Team Meeting | 2016-05-12 | 2016-05-12 | KhoiNguyen | 2 | 2
19 | Review Business Requirements | 2016-05-12 | 2016-05-12 |  | 2 | 4
20 | Review Context Diagram | 2016-06-12 | 2016-06-12 |  | 6 | 5
21 | Training Technical | 2016-06-12 | 2016-06-12 |  | 2 | 2
22 | Customer Meeting | 2016-07-12 | 2016-07-12 |  | 2 | 3
23 | Write Usecase description "Manage Q&A" Function | 2016-07-12 | 2016-08-12 |  | 3 | 5
24 | Write Usecase description "Manage Languages" Function | 2016-07-12 | 2016-08-12 |  | 2 | 2
25 | Draw Usecase Diagram "Manage Homepage" Function | 2016-08-12 | 2016-09-12 |  | 4 | 3
26 | Draw Usecase Diagram "Manage Categories" Function | 2016-08-12 | 2016-09-12 |  | 3 | 4
27 | Team Meeting | 2016-05-12 | 2016-05-12 | MinhDoan | 2 | 2
28 | Review Business Requirements | 2016-05-12 | 2016-05-12 |  | 3 | 4
29 | Review Scope and Limitations | 2016-05-12 | 2016-05-12 |  | 2 | 2
30 | Review Business Context | 2016-05-12 | 2016-05-12 |  | 4 | 5
31 | Collect into Concept of Operation document | 2016-06-12 | 2016-06-12 |  | 1 | 1
32 | Training Technical | 2016-06-12 | 2016-06-12 |  | 2 | 2
33 | Customer Meeting | 2016-07-12 | 2016-07-12 |  | 2 | 3
34 | Write Usecase description "Manage Banners" Function | 2016-07-12 | 2016-08-12 |  | 4 | 4
35 | Write Usecase description "Manage Pop-ups Function | 2016-07-12 | 2016-08-12 |  | 3 | 4
36 | Draw Usecase Diagram "Manage Banners" Function | 2016-08-12 | 2016-09-12 |  | 3 | 3
37 | Draw Usecase Diagram "Manage Pop-ups" Function | 2016-08-12 | 2016-09-12 |  | 2 | 3
38 | Team Meeting | 2016-05-12 | 2016-05-12 | TaiNguyen | 2 | 2
39 | Review Business Context | 2016-05-12 | 2016-05-12 |  | 3 | 5
40 | Review Proposed System | 2016-06-12 | 2016-06-12 |  | 5 | 6
41 | Review prototype for website | 2016-06-12 | 2016-06-12 |  | 5 | 6
42 | Training Technical | 2016-06-12 | 2016-06-12 |  | 2 | 2
43 | Customer Meeting | 2016-07-12 | 2016-07-12 |  | 2 | 3
44 | Write Usecase description "Manage Homepage" Function | 2016-07-12 | 2016-08-12 |  | 5 | 5
45 | Draw Usecase Diagram "Manage Q&A" Function | 2016-08-12 | 2016-09-12 |  | 4 | 4
46 | Team Meeting | 2016-05-12 | 2016-05-12 | XuanThaiHien | 2 | 2
47 | Review Scope and Limitations | 2016-05-12 | 2016-05-12 |  | 2 | 2
48 | Training Technical | 2016-06-12 | 2016-06-12 |  | 2 | 2
49 | Customer Meeting | 2016-07-12 | 2016-07-12 |  | 2 | 3
50 | Write Usecase description "Manage Examination" Function | 2016-07-12 | 2016-08-12 |  | 3 | 3
51 | Draw Usecase Diagram "Manage Examination" Function | 2016-08-12 | 2016-09-12 |  | 3 | 4
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 33 | 35
|  |  |  | HienNguyen | 29 | 33
|  |  |  | KhoiNguyen | 26 | 30
|  |  |  | MinhDoan | 28 | 33
|  |  |  | TaiNguyen | 28 | 33
|  |  |  | XuanThaiHien | 14 | 16

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time