## Sheet1
EFFORT LOG
WEEK: 11
No. | Task | From | To | Estimate Time | Actual Time
1 | Team Meeting | 2016-12-12 | 2016-12-12 | 2 | 2
2 | Review Usecase description "Manage Homepage" Function | 2016-12-12 | 2016-12-12 | 3 | 4
3 | Review Usecase description "Manage Q&A" Function | 13/12/2016 | 13/12/2016 | 3 | 3
4 | Review Usecase description "Manage Languages" Function | 13/12/2016 | 13/12/2016 | 1 | 1
5 | Training Technical | 13/12/2016 | 13/12/2016 | 2 | 2
6 | Review Usecase Diagram "Manage Q&A" Function | 14/12/2016 | 14/12/2016 | 3 | 2
7 | Review Usecase Diagram "Manage Examination" Function | 14/12/2016 | 14/12/2016 | 2 | 3
8 | Collect into Usecase Specification document | 14/12/2016 | 14/12/2016 | 1 | 1
9 | Define Product Functions | 15/12/2016 | 15/12/2016 | 1 | 1
10 | Develop UI "Manage Banners" Function | 16/12/2016 | 17/12/2016 | 3 | 5
11 | Develop UI "Manage Pop-ups" Function | 16/12/2016 | 17/12/2016 | 3 | 5