## Sheet1
EFFORT LOG
WEEK: 11
No. | Task | From | To | Estimate Time | Actual Time
1 | Team Meeting | 2016-12-12 | 2016-12-12 | 2 | 2
2 | Review Usecase description "Manage Homepage" Function | 2016-12-12 | 2016-12-12 | 3 | 2
3 | Review Usecase description "Manage Pop-ups Function | 13/12/2016 | 13/12/2016 | 2 | 2
4 | Review Usecase Diagram "Manage Languages" Function | 14/12/2016 | 14/12/2016 | 2 | 1
5 | Define Business rules | 15/12/2016 | 15/12/2016 | 2 | 1
6 | Develop UI "Manage Examination" Function | 16/12/2016 | 17/12/2016 | 3 | 5