## Report
WEEKLY REPORT
WEEK: 11
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 2016-12-12 | 2016-12-12 | HaiTran | 2 | 2
2 | Review Usecase description "Manage Accounts" Function | 2016-12-12 | 2016-12-12 |  | 5 | 4
3 | Review Usecase description "Manage Banners" Function | 13/12/2016 | 13/12/2016 |  | 2 | 3
4 | Review Usecase description "Manage Categories" Function | 13/12/2016 | 13/12/2016 |  | 5 | 3
5 | Training Technical | 13/12/2016 | 13/12/2016 |  | 2 | 2
6 | Review Usecase Diagram "Manage Homepage" Function | 14/12/2016 | 14/12/2016 |  | 4 | 2
7 | Review Usecase Diagram "Manage Categories" Function | 14/12/2016 | 14/12/2016 |  | 3 | 3
8 | Define Quality Attribute | 15/12/2016 | 15/12/2016 |  | 4 | 3
9 | Develop UI "Manage Accounts" Function | 16/12/2016 | 17/12/2016 |  | 5 | 6
10 | Develop UI "Manage Categories" Function | 16/12/2016 | 17/12/2016 |  | 5 | 8
11 | Team Meeting | 2016-12-12 | 2016-12-12 | HienNguyen | 2 | 2
12 | Review Usecase description "Manage Accounts" Function | 2016-12-12 | 2016-12-12 |  | 4 | 4
13 | Review Usecase description "Manage Pop-ups Function | 13/12/2016 | 13/12/2016 |  | 3 | 2
14 | Review Usecase description "Manage Examination" Function | 13/12/2016 | 13/12/2016 |  | 3 | 4
15 | Training Technical | 13/12/2016 | 13/12/2016 |  | 2 | 2
16 | Review Usecase Diagram "Manage Accouts" Function | 14/12/2016 | 14/12/2016 |  | 4 | 5
17 | Define user classes and characteristics | 15/12/2016 | 15/12/2016 |  | 3 | 3
18 | Develop UI "Manage Q&A" Function | 16/12/2016 | 17/12/2016 |  | 4 | 6
19 | Team Meeting | 2016-12-12 | 2016-12-12 | KhoiNguyen | 2 | 2
20 | Review Usecase description "Manage News" Function | 2016-12-12 | 2016-12-12 |  | 6 | 4
21 | Review Usecase description "Manage Banners" Function | 13/12/2016 | 13/12/2016 |  | 3 | 2
22 | Review Usecase description "Manage Languages" Function | 13/12/2016 | 13/12/2016 |  | 2 | 1
23 | Training Technical | 13/12/2016 | 13/12/2016 |  | 2 | 2
24 | Review Usecase Diagram "Manage Banners" Function | 14/12/2016 | 14/12/2016 |  | 2 | 3
25 | Review Usecase Diagram "Manage Pop-ups" Function | 14/12/2016 | 14/12/2016 |  | 3 | 3
26 | Define Business constraint | 15/12/2016 | 15/12/2016 |  | 1 | 2
27 | Develop UI "Manage Homepage" Function | 16/12/2016 | 17/12/2016 |  | 5 | 7
28 | Develop UI "Manage Languages" Function | 16/12/2016 | 17/12/2016 |  | 2 | 1
29 | Team Meeting | 2016-12-12 | 2016-12-12 | MinhDoan | 2 | 2
30 | Review Usecase description "Manage Homepage" Function | 2016-12-12 | 2016-12-12 |  | 3 | 4
31 | Review Usecase description "Manage Q&A" Function | 13/12/2016 | 13/12/2016 |  | 3 | 3
32 | Review Usecase description "Manage Languages" Function | 13/12/2016 | 13/12/2016 |  | 1 | 1
33 | Training Technical | 13/12/2016 | 13/12/2016 |  | 2 | 2
34 | Review Usecase Diagram "Manage Q&A" Function | 14/12/2016 | 14/12/2016 |  | 3 | 2
35 | Review Usecase Diagram "Manage Examination" Function | 14/12/2016 | 14/12/2016 |  | 2 | 3
36 | Collect into Usecase Specification document | 14/12/2016 | 14/12/2016 |  | 1 | 1
37 | Define Product Functions | 15/12/2016 | 15/12/2016 |  | 1 | 1
38 | Develop UI "Manage Banners" Function | 16/12/2016 | 17/12/2016 |  | 3 | 5
39 | Develop UI "Manage Pop-ups" Function | 16/12/2016 | 17/12/2016 |  | 3 | 5
40 | Team Meeting | 2016-12-12 | 2016-12-12 | TaiNguyen | 2 | 2
41 | Review Usecase description "Manage News" Function | 2016-12-12 | 2016-12-12 |  | 4 | 5
42 | Review Usecase description "Manage Q&A" Function | 13/12/2016 | 13/12/2016 |  | 4 | 3
43 | Review Usecase description "Manage Categories" Function | 13/12/2016 | 13/12/2016 |  | 4 | 5
44 | Training Technical | 13/12/2016 | 13/12/2016 |  | 2 | 2
45 | Review Usecase Diagram "Manage News" Function | 14/12/2016 | 14/12/2016 |  | 6 | 5
46 | Define Operating environment | 15/12/2016 | 15/12/2016 |  | 2 | 1
47 | Develop UI "Manage News" Function | 16/12/2016 | 17/12/2016 |  | 6 | 8
48 | Team Meeting | 2016-12-12 | 2016-12-12 | XuanThaiHien | 2 | 2
49 | Review Usecase description "Manage Homepage" Function | 2016-12-12 | 2016-12-12 |  | 3 | 2
50 | Review Usecase description "Manage Pop-ups Function | 13/12/2016 | 13/12/2016 |  | 2 | 2
51 | Review Usecase Diagram "Manage Languages" Function | 14/12/2016 | 14/12/2016 |  | 2 | 1
52 | Define Business rules | 15/12/2016 | 15/12/2016 |  | 2 | 1
53 | Develop UI "Manage Examination" Function | 16/12/2016 | 17/12/2016 |  | 3 | 5
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 37 | 36
|  |  |  | HienNguyen | 25 | 28
|  |  |  | KhoiNguyen | 28 | 27
|  |  |  | MinhDoan | 24 | 29
|  |  |  | TaiNguyen | 30 | 31
|  |  |  | XuanThaiHien | 14 | 13

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time