## Sheet1
EFFORT LOG
WEEK: 13
No. | Task | From | To | Estimate Time | Actual Time
1 | Team Meeting | 26/12/2016 | 26/12/2016 | 2 | 2
2 | Review "Manage News" Functional Testcase | 26/12/2016 | 26/12/2016 | 4 | 5
3 | Review "Manage Pop-ups" Functional Testcase | 27/12/2016 | 27/12/2016 | 2 | 2
4 | Training Technical | 27/12/2016 | 27/12/2016 | 2 | 2
5 | Review "Manage Account" User Acceptance Testcase | 28/12/2016 | 28/12/2016 | 5 | 6
6 | Review "Manage Banners" User Acceptance Testcase | 28/12/2016 | 28/12/2016 | 2 | 3
7 | Review "Manage Examination" User Acceptance Testcase | 29/12/2016 | 29/12/2016 | 2 | 3
8 | Review "Manage Q&A" User Acceptance Testcase | 29/12/2016 | 29/12/2016 | 2 | 3
9 | Update "Manage News" Functional Testcase | 29/12/2016 | 29/12/2016 | 3 | 3
10 | Research Static view | 30/12/2016 | 31/12/2016 | 5 | 4
11 | Writting rationel | 30/12/2016 | 31/12/2016 | 3 | 1