## Sheet1
EFFORT LOG
WEEK: 13
No. | Task | From | To | Estimate Time | Actual Time
1 | Team Meeting | 26/12/2016 | 26/12/2016 | 2 | 2
2 | Review "Manage News" Functional Testcase | 26/12/2016 | 26/12/2016 | 3 | 6
3 | Review "Manage Categories" Functional Testcase | 27/12/2016 | 27/12/2016 | 3 | 4
4 | Training Technical | 27/12/2016 | 27/12/2016 | 2 | 2
5 | Review "Manage Languages" Functional Testcase | 28/12/2016 | 28/12/2016 | 1 | 2
6 | Review "Manage News" User Acceptance Testcase | 28/12/2016 | 28/12/2016 | 4 | 6
7 | Review "Manage Categories" User Acceptance Testcase | 29/12/2016 | 29/12/2016 | 5 | 6
8 | Review "Manage Languages" User Acceptance Testcase | 29/12/2016 | 29/12/2016 | 1 | 1
9 | Update "Manage Account" Functional Testcase | 29/12/2016 | 29/12/2016 | 2 | 3
10 | Research Physical view | 30/12/2016 | 31/12/2016 | 3 | 5
11 | Draw Physical view draft | 30/12/2016 | 31/12/2016 | 3 | 4