## Sheet1
EFFORT LOG
WEEK: 13
No. | Task | From | To | Estimate Time | Actual Time
1 | Review "Manage Homepage" Functional Testcase | 26/12/2016 | 26/12/2016 | 2 | 2
2 | Review "Manage Banners" Functional Testcase | 27/12/2016 | 27/12/2016 | 3 | 2
3 | Review "Manage Languages" Functional Testcase | 28/12/2016 | 28/12/2016 | 1 | 1
4 | Review "Manage Banners" User Acceptance Testcase | 28/12/2016 | 28/12/2016 | 2 | 1
5 | Review "Manage Pop-ups" User Acceptance Testcase | 29/12/2016 | 29/12/2016 | 2 | 1
6 | Update "Manage Examination" Functional Testcase | 29/12/2016 | 29/12/2016 | 3 | 3
7 | Update "Manage Q&A" Functional Testcase | 29/12/2016 | 29/12/2016 | 3 | 2
8 | Research Dynamic view | 30/12/2016 | 31/12/2016 | 3 | 4