## Report
WEEKLY REPORT
WEEK: 14
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 2017-02-01 | 2017-02-01 | HaiTran | 2 | 2
2 | Draw Static View Level 1 | 2017-02-01 | 2017-02-01 |  | 5 | 6
3 | Draw Static View Level 2 | 2017-02-01 | 2017-02-01 |  | 4 | 3
4 | Mentor Meeting | 2017-03-01 | 2017-03-01 |  | 3 | 2
5 | Training Technical | 2017-03-01 | 2017-03-01 |  | 2 | 2
6 | Draw Static View Level 1 | 2017-03-01 | 2017-03-01 |  | 4 | 3
7 | Draw Static View Level 2 | 2017-03-01 | 2017-03-01 |  | 4 | 4
8 | Review Physical View | 2017-04-01 | 2017-04-01 |  | 2 | 2
9 | Review Static View | 2017-04-01 | 2017-04-01 |  | 3 | 2
10 | Review Dynamic | 2017-04-01 | 2017-05-01 |  | 2 | 3
11 | Mentor Meeting | 2017-05-01 | 2017-05-01 |  | 2 | 4
12 | Team Meeting | 2017-02-01 | 2017-02-01 | HienNguyen | 2 | 2
13 | Draw Physical View | 2017-02-01 | 2017-02-01 |  | 4 | 7
14 | Mentor Meeting | 2017-03-01 | 2017-03-01 |  | 3 | 2
15 | Training Technical | 2017-03-01 | 2017-03-01 |  | 2 | 2
16 | Draw Physical View | 2017-03-01 | 2017-03-01 |  | 3 | 3
17 | Review Physical View | 2017-04-01 | 2017-04-01 |  | 2 | 2
18 | Review Static View | 2017-04-01 | 2017-04-01 |  | 2 | 2
19 | Review Dynamic | 2017-04-01 | 2017-05-01 |  | 3 | 3
20 | Mentor Meeting | 2017-05-01 | 2017-05-01 |  | 2 | 4
21 | Research pattern 3 layers in dynamic view | 2017-06-01 | 2017-07-01 |  | 3 | 2
22 | Team Meeting | 2017-02-01 | 2017-02-01 | KhoiNguyen | 2 | 2
23 | Draw Static View Level 2 | 2017-02-01 | 2017-02-01 |  | 6 | 5
24 | Mentor Meeting | 2017-03-01 | 2017-03-01 |  | 3 | 2
25 | Training Technical | 2017-03-01 | 2017-03-01 |  | 2 | 2
26 | Draw Static View Level 2 | 2017-03-01 | 2017-03-01 |  | 5 | 4
27 | Review Physical View | 2017-04-01 | 2017-04-01 |  | 2 | 2
28 | Review Static View | 2017-04-01 | 2017-04-01 |  | 2 | 2
29 | Review Dynamic | 2017-04-01 | 2017-05-01 |  | 3 | 3
30 | Mentor Meeting | 2017-05-01 | 2017-05-01 |  | 2 | 4
31 | Research pattern 3 layers in dynamic view | 2017-06-01 | 2017-07-01 |  | 2 | 1
32 | Update Dynamic View | 2017-06-01 | 2017-07-01 |  | 2 | 4
33 | Team Meeting | 2017-02-01 | 2017-02-01 | MinhDoan | 2 | 2
34 | Draw Dynamic View Level 2 | 2017-02-01 | 2017-02-01 |  | 6 | 8
35 | Mentor Meeting | 2017-03-01 | 2017-03-01 |  | 3 | 2
36 | Training Technical | 2017-03-01 | 2017-03-01 |  | 2 | 2
37 | Draw Dynamic View Level 2 | 2017-03-01 | 2017-03-01 |  | 5 | 3
38 | Review Physical View | 2017-04-01 | 2017-04-01 |  | 2 | 2
39 | Review Static View | 2017-04-01 | 2017-04-01 |  | 3 | 2
40 | Review Dynamic | 2017-04-01 | 2017-05-01 |  | 2 | 3
41 | Mentor Meeting | 2017-05-01 | 2017-05-01 |  | 2 | 4
42 | Research tactics for physical view | 2017-06-01 | 2017-07-01 |  | 1 | 2
43 | Research tactics for quality attributes | 2017-06-01 | 2017-07-01 |  | 3 | 4
44 | Team Meeting | 2017-02-01 | 2017-02-01 | TaiNguyen | 2 | 2
45 | Draw Dynamic View Level 1 | 2017-02-01 | 2017-02-01 |  | 7 | 9
46 | Mentor Meeting | 2017-03-01 | 2017-03-01 |  | 3 | 2
47 | Training Technical | 2017-03-01 | 2017-03-01 |  | 2 | 2
48 | Draw Dynamic View Level 1 | 2017-03-01 | 2017-03-01 |  | 3 | 4
49 | Review Physical View | 2017-04-01 | 2017-04-01 |  | 2 | 2
50 | Review Static View | 2017-04-01 | 2017-04-01 |  | 4 | 2
51 | Review Dynamic | 2017-04-01 | 2017-05-01 |  | 2 | 3
52 | Mentor Meeting | 2017-05-01 | 2017-05-01 |  | 2 | 4
53 | Update Static View | 2017-06-01 | 2017-07-01 |  | 2 | 3
54 | Update Physical View | 2017-06-01 | 2017-07-01 |  | 2 | 2.5
55 | Team Meeting | 2017-02-01 | 2017-02-01 | XuanThaiHien | 2 | 2
56 | Mentor Meeting | 2017-03-01 | 2017-03-01 |  | 3 | 2
57 | Review Physical View | 2017-04-01 | 2017-04-01 |  | 2 | 2
58 | Review Static View | 2017-04-01 | 2017-04-01 |  | 2 | 2
59 | Review Dynamic | 2017-04-01 | 2017-05-01 |  | 2 | 3
60 | Mentor Meeting | 2017-05-01 | 2017-05-01 |  | 2 | 4
61 | Apply tactics performance, usability for physical view | 2017-06-01 | 2017-07-01 |  | 1 | 2
62 | Tactics performance, usability for physical view | 2017-06-01 | 2017-07-01 |  | 5 | 2
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 33 | 33
|  |  |  | HienNguyen | 26 | 29
|  |  |  | KhoiNguyen | 31 | 29
|  |  |  | MinhDoan | 31 | 34
|  |  |  | TaiNguyen | 31 | 35.5
|  |  |  | XuanThaiHien | 19 | 19

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time