## Sheet1
EFFORT LOG
WEEK: 16
No. | Task | From | To | Estimate Time | Actual Time
1 | Team Meeting | 16/1/2017 | 16/1/2017 | 2 | 2
2 | Draw class diagram function "Manage Homepage" | 16/1/2017 | 16/1/2017 | 6 | 5
3 | Training Technical | 17/1/2017 | 17/1/2017 | 2 | 2
4 | Draw sequence diagram function "Manage News" | 17/1/2017 | 17/1/2017 | 5 | 6
5 | Mentor Meeting | 19/1/2017 | 19/1/2017 | 2 | 3
6 | Review class diagram function "Manage News" | 19/1/2017 | 19/1/2017 | 2 | 2
7 | Review sequence diagram function "Manage Categories" | 20/1/2017 | 20/1/2017 | 2 | 2
8 | Review sequence diagram function "Manage Language" | 20/1/2017 | 20/1/2017 | 2 | 1
9 | Update sequence diagram function "Manage Categories" | 21/1/2017 | 21/1/2017 | 4 | 4