## Sheet1
EFFORT LOG
WEEK: 16
No. | Task | From | To | Estimate Time | Actual Time
1 | Team Meeting | 16/1/2017 | 16/1/2017 | 2 | 2
2 | Draw class diagram function "Manage FAQ" | 16/1/2017 | 16/1/2017 | 7 | 6
3 | Training Technical | 17/1/2017 | 17/1/2017 | 2 | 2
4 | Draw class diagram function "Manage Popups" | 17/1/2017 | 17/1/2017 | 7 | 6
5 | Draw sequence diagram function "Manage Categories" | 18/1/2017 | 18/1/2017 | 7 | 8
6 | Draw sequence diagram function "Manage Popups" | 18/1/2017 | 18/1/2017 | 7 | 8
7 | Mentor Meeting | 19/1/2017 | 19/1/2017 | 2 | 3
8 | Review class diagram function "Manage FAQ" | 19/1/2017 | 19/1/2017 | 2 | 1
9 | Review class diagram function "Manage Homepage" | 19/1/2017 | 19/1/2017 | 2 | 2
10 | Review class diagram function "Manage Examination" | 20/1/2017 | 20/1/2017 | 2 | 3
11 | Review sequence diagram function "Manage Categories" | 20/1/2017 | 20/1/2017 | 2 | 3
12 | Review sequence diagram function "Manage Homepage" | 20/1/2017 | 20/1/2017 | 3 | 2
13 | Collect diagram into document | 21/1/2017 | 21/1/2017 | 2 | 2