## Report
WEEKLY REPORT
WEEK: 17
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 23/1/2017 | 23/1/2017 | HaiTran | 2 | 2
2 | Mentor Meeting | 23/1/2017 | 23/1/2017 |  | 3 | 4
3 | Training Technical | 24/1/2017 | 24/1/2017 |  | 2 | 2
4 | Create "Categories" table | 24/1/2017 | 24/1/2017 |  | 3 | 3
5 | Create "Homepage" table | 24/1/2017 | 24/1/2017 |  | 3 | 3
6 | Implement Create Account Function | 24/1/2017 | 24/1/2017 |  | 3 | 4
7 | Implement server | 25/1/2017 | 27/1/2017 |  | 20 | 22
8 | Implement Login Function | 27/1/2017 | 28/1/2017 |  | 7 | 8
9 | Team Meeting | 23/1/2017 | 23/1/2017 | HienNguyen | 2 | 2
10 | Mentor Meeting | 23/1/2017 | 23/1/2017 |  | 3 | 4
11 | Training Technical | 24/1/2017 | 24/1/2017 |  | 2 | 2
12 | Create "News" table | 24/1/2017 | 24/1/2017 |  | 3 | 3
13 | Create "Language" table | 24/1/2017 | 24/1/2017 |  | 2 | 1
14 | Implement Create Account Function | 24/1/2017 | 24/1/2017 |  | 4 | 4
15 | Implement connection from Redis to MongoDB | 25/1/2017 | 26/1/2017 |  | 15 | 16
16 | Implement Login Function | 27/1/2017 | 28/1/2017 |  | 6 | 6
17 | Team Meeting | 23/1/2017 | 23/1/2017 | KhoiNguyen | 2 | 2
18 | Mentor Meeting | 23/1/2017 | 23/1/2017 |  | 3 | 4
19 | Training Technical | 24/1/2017 | 24/1/2017 |  | 2 | 2
20 | Create "Banners" table | 24/1/2017 | 24/1/2017 |  | 4 | 2
21 | Create "Popups" table | 24/1/2017 | 24/1/2017 |  | 4 | 2
22 | Implement Create Account Function | 24/1/2017 | 24/1/2017 |  | 5 | 4
23 | Implement server | 25/1/2017 | 27/1/2017 |  | 24 | 16
24 | Implement Login Function | 27/1/2017 | 28/1/2017 |  | 7 | 7
25 | Team Meeting | 23/1/2017 | 23/1/2017 | MinhDoan | 2 | 2
26 | Mentor Meeting | 23/1/2017 | 23/1/2017 |  | 3 | 4
27 | Training Technical | 24/1/2017 | 24/1/2017 |  | 2 | 2
28 | Create "Examination" table | 24/1/2017 | 24/1/2017 |  | 3 | 3
29 | Create "FAQ" table | 24/1/2017 | 24/1/2017 |  | 3 | 3
30 | Implement Create Account Function | 24/1/2017 | 24/1/2017 |  | 3
31 | Implement connection to MongoDB | 25/1/2017 | 27/1/2016 |  | 14 | 16
32 | Implement Login Function | 27/1/2017 | 28/1/2017 |  | 6
33 | Team Meeting | 23/1/2017 | 23/1/2017 | TaiNguyen | 2 | 2
34 | Mentor Meeting | 23/1/2017 | 23/1/2017 |  | 3 | 4
35 | Training Technical | 24/1/2017 | 24/1/2017 |  | 2 | 2
36 | Create "Account" table | 24/1/2017 | 24/1/2017 |  | 4 | 3
37 | Implement Create Account Function | 24/1/2017 | 24/1/2017 |  | 4 | 3
38 | Implement connection from ElasticSearch to MongoDB | 25/1/2017 | 27/1/2016 |  | 22 | 25
39 | Implement Login Function | 27/1/2017 | 28/1/2017 |  | 6 | 7
40 | Implement Create Account Function | 24/1/2017 | 24/1/2017 | XuanThaiHien | 4
41 | Implement Login Function | 27/1/2017 | 28/1/2017 |  | 7
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 43 | 48
|  |  |  | HienNguyen | 37 | 38
|  |  |  | KhoiNguyen | 51 | 39
|  |  |  | MinhDoan | 36 | 30
|  |  |  | TaiNguyen | 43 | 46
|  |  |  | XuanThaiHien | 11 | 0

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time