## Report
WEEKLY REPORT
WEEK: 2
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 2016-10-10 | 2016-10-10 | HaiTran | 1 | 2
2 | Review Process Decision | 2016-11-10 | 2016-11-10 |  | 2 | 5
3 | Mentor Meeting | 2016-12-10 | 2016-12-10 |  | 1 | 2
4 | Review SWOT Project | 13/10/2016 | 13/10/2016 |  | 2 | 3
5 | Define SWOT individual | 13/10/2016 | 14/10/2016 |  | 1 | 1
6 | Team Meeting | 2016-10-10 | 2016-10-10 | HienNguyen | 1 | 2
7 | Review Process Decision | 2016-11-10 | 2016-11-10 |  | 3 | 5
8 | Mentor Meeting | 2016-12-10 | 2016-12-10 |  | 1 | 2
9 | Update Project Charter | 13/10/2016 | 14/12/2016 |  | 4 | 2
10 | Define SWOT individual | 13/10/2016 | 14/10/2016 |  | 2 | 1
11 | Team Meeting | 2016-10-10 | 2016-10-10 | KhoiNguyen | 1 | 2
12 | Review Process Decision | 2016-11-10 | 2016-11-10 |  | 3 | 5
13 | Mentor Meeting | 2016-12-10 | 2016-12-10 |  | 1 | 2
14 | Define SWOT technology | 2016-12-10 | 13/10/2016 |  | 3 | 2
15 | Review SWOT technology | 13/10/2016 | 13/10/2016 |  | 2 | 3
16 | Define SWOT individual | 13/10/2016 | 14/10/2016 |  | 2 | 2
17 | Team Meeting | 2016-10-10 | 2016-10-10 | MinhDoan | 1 | 2
18 | Review Process Decision | 2016-11-10 | 2016-11-10 |  | 2 | 5
19 | Mentor Meeting | 2016-12-10 | 2016-12-10 |  | 1 | 2
20 | Define SWOT individual | 13/10/2016 | 14/10/2016 |  | 2 | 2
21 | Team Meeting | 2016-10-10 | 2016-10-10 | TaiNguyen | 1 | 2
22 | Review Process Decision | 2016-11-10 | 2016-11-10 |  | 3 | 5
23 | Mentor Meeting | 2016-12-10 | 2016-12-10 |  | 1 | 2
24 | Define SWOT Project | 2016-12-10 | 13/10/2016 |  | 2 | 3
25 | Review SWOT technology | 13/10/2016 | 13/10/2016 |  | 1 | 3
26 | Review SWOT Project | 13/10/2016 | 13/10/2016 |  | 1 | 3
27 | Define SWOT individual | 13/10/2016 | 14/10/2016 |  | 2 | 1
28 | Update Process Decision | 14/10/2016 | 15/10/2016 |  | 3 | 4
29 | Team Meeting | 2016-10-10 | 2016-10-10 | XuanThaiHien | 1 | 2
30 | Review Process Decision | 2016-11-10 | 2016-11-10 |  | 3 | 5
31 | Mentor Meeting | 2016-12-10 | 2016-12-10 |  | 1 | 2
32 | Define SWOT individual | 13/10/2016 | 14/10/2016 |  | 2 | 1
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 7 | 13
|  |  |  | HienNguyen | 11 | 12
|  |  |  | KhoiNguyen | 12 | 16
|  |  |  | MinhDoan | 6 | 11
|  |  |  | TaiNguyen | 14 | 23
|  |  |  | XuanThaiHien | 7 | 10

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time