## Report
WEEKLY REPORT
WEEK: 20
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 13/2/2017 | 13/2/2017 | HaiTran | 2 | 2
2 | Implement "Create draft" function | 13/2/2017 | 14/2/2017 |  | 12 | 14
3 | Demo "View News" function | 13/2/2017 | 13/2/2017 |  | 2 | 2
4 | Training Technical | 14/2/2017 | 14/2/2017 |  | 2 | 2
5 | Demo "Create Draft" function | 14/2/2017 | 14/2/2017 |  | 1 | 2
6 | Demo "Edit News" function | 14/2/2017 | 14/2/2017 |  | 1 | 3
7 | Mentor Meeting | 15/2/2017 | 15/2/2017 |  | 2 | 4
8 | Implement "Sort News" function | 16/2/2017 | 18/2/2017 |  | 16 | 17
9 | Team Meeting | 13/2/2017 | 13/2/2017 | HienNguyen | 2 | 2
10 | Demo "View News" function | 13/2/2017 | 13/2/2017 |  | 2 | 2
11 | Training Technical | 14/2/2017 | 14/2/2017 |  | 2 | 2
12 | Demo "Create Draft" function | 14/2/2017 | 14/2/2017 |  | 1 | 2
13 | Demo "Edit News" function | 14/2/2017 | 14/2/2017 |  | 1 | 3
14 | Mentor Meeting | 15/2/2017 | 15/2/2017 |  | 2 | 4
15 | Implement "Deactivate News" function | 16/2/2017 | 18/2/2017 |  | 16 | 18
16 | Team Meeting | 13/2/2017 | 13/2/2017 | KhoiNguyen | 2 | 2
17 | Implement"Edit News" function | 13/2/2017 | 14/2/2017 |  | 14 | 16
18 | Demo "View News" function | 13/2/2017 | 13/2/2017 |  | 2 | 2
19 | Training Technical | 14/2/2017 | 14/2/2017 |  | 2 | 2
20 | Demo "Create Draft" function | 14/2/2017 | 14/2/2017 |  | 1 | 2
21 | Demo "Edit News" function | 14/2/2017 | 14/2/2017 |  | 1 | 3
22 | Mentor Meeting | 15/2/2017 | 15/2/2017 |  | 2 | 4
23 | Implement "Search News" function | 16/2/2017 | 18/2/2017 |  | 17 | 16
24 | Team Meeting | 13/2/2017 | 13/2/2017 | MinhDoan | 2 | 2
25 | Demo "View News" function | 13/2/2017 | 13/2/2017 |  | 2 | 2
26 | Training Technical | 14/2/2017 | 14/2/2017 |  | 2 | 2
27 | Demo "Create Draft" function | 14/2/2017 | 14/2/2017 |  | 1 | 2
28 | Demo "Edit News" function | 14/2/2017 | 14/2/2017 |  | 1 | 3
29 | Mentor Meeting | 15/2/2017 | 15/2/2017 |  | 2 | 4
30 | Team Meeting | 13/2/2017 | 13/2/2017 | TaiNguyen | 2 | 2
31 | Implement "Transfer News" function | 13/2/2017 | 14/2/2017 |  | 15 | 16
32 | Demo "View News" function | 13/2/2017 | 13/2/2017 |  | 2 | 2
33 | Training Technical | 14/2/2017 | 14/2/2017 |  | 2 | 2
34 | Demo "Create Draft" function | 14/2/2017 | 14/2/2017 |  | 1 | 2
35 | Demo "Edit News" function | 14/2/2017 | 14/2/2017 |  | 1 | 3
36 | Mentor Meeting | 15/2/2017 | 15/2/2017 |  | 2 | 4
37 | Implement "Approve News" function | 16/2/2017 | 18/2/2017 |  | 14 | 17
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 38 | 46
|  |  |  | HienNguyen | 26 | 33
|  |  |  | KhoiNguyen | 41 | 47
|  |  |  | MinhDoan | 10 | 15
|  |  |  | TaiNguyen | 39 | 48
|  |  |  | XuanThaiHien | 0 | 0

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time