## Sheet1
EFFORT LOG
WEEK: 21
No. | Task | From | To | Estimate Time | Actual Time
1 | Implement "View News" function on server | 20/2/2017 | 22/2/2017 | 14 | 16
2 | Implement "View News" function on frontend for user | 20/2/2017 | 22/2/2017 | 20 | 18
3 | Training Technical | 23/2/2017 | 23/2/2017 | 2 | 2
4 | Implement "Transfer News" function on frontend | 23/2/2017 | 24/2/2017 | 6 | 6
5 | Implement "Edit News"function on frontend | 23/2/2017 | 24/2/2017 | 4 | 5
6 | Mentor Meeting | 24/2/2017 | 24/2/2017 | 2 | 3
7 | Presentation EOMP2 | 25/2/2017 | 25/2/2017 | 2 | 2
8 | Team Meeting | 25/2/2017 | 25/2/2017 | 1 | 1