## Report
WEEKLY REPORT
WEEK: 22
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 27/2/2017 | 27/2/2017 | HaiTran | 2 | 2
2 | Implement "Approve News" function on server | 27/2/2017 | 28/2/2017 |  | 10 | 13
3 | Implement "Deactive News" function on frontend | 27/2/2017 | 28/2/2017 |  | 8 | 5
4 | Training Technical | 2017-01-03 | 2017-01-03 |  | 2 | 2
5 | Implement "Search News" function on server | 2017-01-03 | 2017-03-03 |  | 15 | 14
6 | Mentor Meeting | 2017-03-03 | 2017-03-03 |  | 2 | 2
7 | Implement "View categories" function on server | 2017-04-03 | 2017-04-03 |  | 10 | 12
8 | Implement "View categories" function on frontend | 2017-04-03 | 2017-04-03 |  | 9 | 8
9 | Team Meeting | 27/2/2017 | 27/2/2017 | HienNguyen | 2 | 2
10 | Implement "Approve News" function on server | 27/2/2017 | 28/2/2017 |  | 13 | 15
11 | Implement "Deactive News" function on server | 27/2/2017 | 28/2/2017 |  | 8 | 7
12 | Training Technical | 2017-01-03 | 2017-01-03 |  | 2 | 2
13 | Implement "Search News" function on server | 2017-01-03 | 2017-03-03 |  | 15 | 16
14 | Implement "Sort News" function on server | 2017-01-03 | 2017-03-03 |  | 14 | 16
15 | Mentor Meeting | 2017-03-03 | 2017-03-03 |  | 2 | 2
16 | Implement "View categories" function on server | 2017-04-03 | 2017-04-03 |  | 10 | 10
17 | Team Meeting | 27/2/2017 | 27/2/2017 | KhoiNguyen | 2 | 2
18 | Implement "Approve News" function on frontend | 27/2/2017 | 28/2/2017 |  | 12 | 10
19 | Implement "Deactive News" function on server | 27/2/2017 | 28/2/2017 |  | 7 | 5
20 | Training Technical | 2017-01-03 | 2017-01-03 |  | 2 | 2
21 | Implement "Sort News" function on server | 2017-01-03 | 2017-03-03 |  | 12 | 10
22 | Mentor Meeting | 2017-03-03 | 2017-03-03 |  | 2 | 2
23 | Import data into database for function "Manage Categories" | 2017-04-03 | 2017-04-03 |  | 6 | 5
24 | Team Meeting | 27/2/2017 | 27/2/2017 | MinhDoan | 2 | 2
25 | Training Technical | 2017-01-03 | 2017-01-03 |  | 2 | 2
26 | Mentor Meeting | 2017-03-03 | 2017-03-03 |  | 2 | 2
27 | Team Meeting | 27/2/2017 | 27/2/2017 | TaiNguyen | 2 | 2
28 | Implement "Approve News" function on frontend | 27/2/2017 | 28/2/2017 |  | 12 | 13
29 | Training Technical | 2017-01-03 | 2017-01-03 |  | 2 | 2
30 | Implement "Search News" function on frontend | 2017-01-03 | 2017-03-03 |  | 17 | 18
31 | Implement "Sort News" function on frontend | 2017-01-03 | 2017-03-03 |  | 13 | 13
32 | Mentor Meeting | 2017-03-03 | 2017-03-03 |  | 2 | 2
33 | Implement "View categories" function on frontend | 2017-04-03 | 2017-04-03 |  | 10 | 10
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 58 | 58
|  |  |  | HienNguyen | 66 | 70
|  |  |  | KhoiNguyen | 43 | 36
|  |  |  | MinhDoan | 6 | 6
|  |  |  | TaiNguyen | 58 | 60
|  |  |  | XuanThaiHien | 0 | 0

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time