## Report
WEEKLY REPORT
WEEK: 3
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Mentor Meeting | 17/10/2016 | 17/10/2016 | HaiTran | 2 | 5
2 | Team Meeting | 18/10/2016 | 18/10/2016 |  | 2 | 2
3 | Define effort log template | 18/10/2016 | 20/10/2016 |  | 1 | 2
4 | Define weekly report template | 18/10/2016 | 20/10/2016 |  | 1 | 2
5 | Define WBS template | 19/10/2016 | 20/10/2016 |  | 4 | 4
6 | Define requirement management plan template | 19/10/2016 | 20/10/2016 |  | 3 | 5
7 | Review Project Plan Template | 20/10/2016 | 21/10/2016 |  | 3 | 4
8 | Review Architecture and Design Plan Template | 20/10/2016 | 21/10/2016 |  | 6 | 5
9 | Define project plan template | 18/10/2016 | 20/10/2016 | HienNguyen | 4 | 6
10 | Define communication plan template | 18/10/2016 | 20/10/2016 |  | 2 | 3
11 | Define achitecture and design plan template | 19/10/2016 | 20/10/2016 |  | 3 | 3
12 | Review Change Management Template | 20/10/2016 | 21/10/2016 |  | 5 | 5
13 | Mentor Meeting | 17/10/2016 | 17/10/2016 | KhoiNguyen | 2 | 5
14 | Team Meeting | 18/10/2016 | 18/10/2016 |  | 2 | 2
15 | Define configuration template | 18/10/2016 | 20/10/2016 |  | 3 | 6
16 | Review Communication Plan Template | 20/10/2016 | 21/10/2016 |  | 3 | 1
17 | Update Configuration Plan Tempate | 22/10/2016 | 22/10/2016 |  | 2 | 2
18 | Mentor Meeting | 17/10/2016 | 17/10/2016 | MinhDoan | 2 | 5
19 | Team Meeting | 18/10/2016 | 18/10/2016 |  | 2 | 2
20 | Define change management template | 18/10/2016 | 20/10/2016 |  | 5 | 8
21 | Review Measurement Plan Template | 20/10/2016 | 21/10/2016 |  | 2 | 4
22 | Mentor Meeting | 17/10/2016 | 17/10/2016 | TaiNguyen | 2 | 5
23 | Mentor Meeting | 17/10/2016 | 17/10/2016 |  | 2 | 5
24 | Team Meeting | 18/10/2016 | 18/10/2016 |  | 2 | 2
25 | Team Meeting | 18/10/2016 | 18/10/2016 |  | 2 | 2
26 | Define measurement plan template | 18/10/2016 | 20/10/2016 |  | 3 | 5
27 | Review Configuration Template | 20/10/2016 | 21/10/2016 |  | 4 | 4
28 | Review Risk Management Plan Template | 20/10/2016 | 21/10/2016 |  | 3 | 4
29 | Mentor Meeting | 17/10/2016 | 17/10/2016 | XuanThaiHien | 2 | 5
30 | Team Meeting | 18/10/2016 | 18/10/2016 |  | 2 | 2
31 | Define risk management plan template | 19/10/2016 | 20/10/2016 |  | 3 | 4
32 | Review Requirement Management Plan Template | 20/10/2016 | 21/10/2016 |  | 3 | 3
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 22 | 29
|  |  |  | HienNguyen | 14 | 17
|  |  |  | KhoiNguyen | 12 | 16
|  |  |  | MinhDoan | 11 | 19
|  |  |  | TaiNguyen | 18 | 27
|  |  |  | XuanThaiHien | 10 | 14

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time