## Report
WEEKLY REPORT
WEEK: 4
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 24/10/2016 | 24/10/2016 | HaiTran | 3 | 3
2 | Define user acceptance testcase template | 25/10/2016 | 27/10/2016 |  | 4 | 5
3 | Review Vision and Scope Template | 28/10/2016 | 28/10/2016 |  | 2 | 3
4 | Develop Requirement Plan | 28/10/2016 | 29/10/2016 |  | 10 | 9
5 | Define function testcase template | 25/10/2016 | 27/10/2016 | HienNguyen | 2 | 4
6 | Update SRS Template | 28/10/2016 | 29/10/2016 |  | 2 | 2
7 | Develop Implement Plan | 28/10/2016 | 29/10/2016 |  | 9 | 7
8 | Develop Architecture and Design Plan | 28/10/2016 | 29/10/2016 |  | 14 | 11
9 | Team Meeting | 24/10/2016 | 24/10/2016 | KhoiNguyen | 3 | 3
10 | Define concept of operation template | 25/10/2016 | 27/10/2016 |  | 3 | 5
11 | Update Concept of Operation Template | 28/10/2016 | 29/10/2016 |  | 3 | 1
12 | Develop Implement Plan | 28/10/2016 | 29/10/2016 |  | 8 | 5
13 | Team Meeting | 24/10/2016 | 24/10/2016 | MinhDoan | 3 | 3
14 | Define vision and scope template | 25/10/2016 | 27/10/2016 |  | 3 | 4
15 | Define SRS template | 25/10/2016 | 27/10/2016 |  | 4 | 4
16 | Review Test Plan Template | 28/10/2016 | 28/10/2016 |  | 3 | 4
17 | Review Concept of Operation Template | 28/10/2016 | 28/10/2016 |  | 4 | 3
18 | Update Vision and Scope Template | 28/10/2016 | 29/10/2016 |  | 1 | 2
19 | Team Meeting | 24/10/2016 | 24/10/2016 | TaiNguyen | 3 | 3
20 | Team Meeting | 24/10/2016 | 24/10/2016 |  | 3 | 3
21 | Define detail design template | 25/10/2016 | 27/10/2016 |  | 3 | 5
22 | Review SRS Template | 28/10/2016 | 28/10/2016 |  | 3 | 3
23 | Develop Work Break Down Structure | 28/10/2016 | 29/10/2016 |  | 8 | 6
24 | Team Meeting | 24/10/2016 | 24/10/2016 | XuanThaiHien | 3 | 3
25 | Define test plan template | 25/10/2016 | 27/10/2016 |  | 6 | 8
26 | Define test report template | 25/10/2016 | 27/10/2016 |  | 3 | 4
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 19 | 20
|  |  |  | HienNguyen | 27 | 24
|  |  |  | KhoiNguyen | 17 | 14
|  |  |  | MinhDoan | 18 | 20
|  |  |  | TaiNguyen | 20 | 20
|  |  |  | XuanThaiHien | 12 | 15

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time