## Report
WEEKLY REPORT
WEEK: 6
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 2016-07-11 | 2016-07-11 | HaiTran | 2 | 2
2 | Mentor Meeting | 2016-08-11 | 2016-08-11 |  | 2 | 3
3 | Training Technical | 2016-08-11 | 2016-08-11 |  |  | 2
4 | Update Software Development Process | 2016-08-11 | 2016-08-11 |  | 3 | 2
5 | Review Change Management Plan | 2016-12-11 | 2016-12-11 |  | 3 | 3
6 | Review Risk Management Plan | 2016-12-11 | 2016-12-11 |  | 3 | 2
7 | Review Measurement Plan | 2016-12-11 | 2016-12-11 |  | 1 | 2
8 | Team Meeting | 2016-07-11 | 2016-07-11 | HienNguyen | 3 | 2
9 | Mentor Meeting | 2016-08-11 | 2016-08-11 |  | 2 | 3
10 | Training Technical | 2016-08-11 | 2016-08-11 |  |  | 2
11 | Update Schedule | 2016-08-11 | 2016-08-11 |  | 3 | 2
12 | Review Change Management Plan | 2016-12-11 | 2016-12-11 |  | 3 | 3
13 | Review Risk Management Plan | 2016-12-11 | 2016-12-11 |  | 2 | 2
14 | Review Measurement Plan | 2016-12-11 | 2016-12-11 |  | 3 | 2
15 | Team Meeting | 2016-07-11 | 2016-07-11 | KhoiNguyen | 1 | 2
16 | Mentor Meeting | 2016-08-11 | 2016-08-11 |  | 2 | 3
17 | Training Technical | 2016-08-11 | 2016-08-11 |  |  | 2
18 | Review Change Management Plan | 2016-12-11 | 2016-12-11 |  | 3 | 3
19 | Review Risk Management Plan | 2016-12-11 | 2016-12-11 |  | 4 | 2
20 | Review Measurement Plan | 2016-12-11 | 2016-12-11 |  | 2 | 2
21 | Team Meeting | 2016-07-11 | 2016-07-11 | MinhDoan | 3 | 2
22 | Mentor Meeting | 2016-08-11 | 2016-08-11 |  | 3 | 3
23 | Training Technical | 2016-08-11 | 2016-08-11 |  |  | 2
24 | Develop Change Management Plan | 2016-08-11 | 2016-11-11 |  | 10 | 14
25 | Review Change Management Plan | 2016-12-11 | 2016-12-11 |  | 2 | 3
26 | Review Risk Management Plan | 2016-12-11 | 2016-12-11 |  | 3 | 2
27 | Review Measurement Plan | 2016-12-11 | 2016-12-11 |  | 2 | 2
28 | Team Meeting | 2016-07-11 | 2016-07-11 | TaiNguyen | 3 | 2
29 | Mentor Meeting | 2016-08-11 | 2016-08-11 |  | 3 | 3
30 | Training Technical | 2016-08-11 | 2016-08-11 |  |  | 2
31 | Update Training Plan | 2016-08-11 | 2016-08-11 |  | 2 | 1
32 | Develop Measurement plan | 2016-08-11 | 2016-11-11 |  | 4 | 5
33 | Review Change Management Plan | 2016-12-11 | 2016-12-11 |  | 4 | 3
34 | Review Risk Management Plan | 2016-12-11 | 2016-12-11 |  | 2 | 2
35 | Review Measurement Plan | 2016-12-11 | 2016-12-11 |  | 3 | 2
36 | Team Meeting | 2016-07-11 | 2016-07-11 | XuanThaiHien | 2 | 2
37 | Mentor Meeting | 2016-08-11 | 2016-08-11 |  | 3 | 3
38 | Training Technical | 2016-08-11 | 2016-08-11 |  |  | 2
39 | Develop Risk Management Plan | 2016-08-11 | 2016-11-11 |  | 16 | 15
40 | Review Change Management Plan | 2016-12-11 | 2016-12-11 |  | 4 | 3
41 | Review Risk Management Plan | 2016-12-11 | 2016-12-11 |  | 3 | 2
42 | Review Measurement Plan | 2016-12-11 | 2016-12-11 |  | 2 | 2
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 14 | 16
|  |  |  | HienNguyen | 16 | 16
|  |  |  | KhoiNguyen | 12 | 14
|  |  |  | MinhDoan | 23 | 28
|  |  |  | TaiNguyen | 21 | 20
|  |  |  | XuanThaiHien | 30 | 29

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time