## Sheet1
EFFORT LOG
WEEK: 9
No. | Task | From | To | Estimate Time | Actual Time
1 | Team Meeting | 28/11/2016 | 28/11/2016 |  | 3
2 | Review Business Workflow "Manage News" function | 28/11/2016 | 28/11/2016 | 3 | 4
3 | Review Business Workflow "Manage FAQ" function | 29/11/2016 | 29/11/2016 | 4 | 2
4 | Review Business Workflow "Manage Languages" function | 29/11/2016 | 29/11/2016 | 1 | 1
5 | Training Technical | 29/11/2016 | 29/11/2016 | 2 | 2
6 | Update Business workflow "Manage FAQ" function | 30/11/2016 | 2016-01-12 | 4 | 5
7 | Define Scope and Limitations | 2016-01-12 | 2016-01-12 | 3 | 6
8 | Define Justification of Changes | 2016-02-12 | 2016-03-12 | 2 | 5