## General
Introduce - This document is the consent form for the admissions website made by BSS team. This document provides clear and detailed information about the features of "Van Lang Admission" project. - Through this document, Users will review the software that meets the requirements as agreed at the beginning or not?
User Acceptance Test for <VanLang Admission Project>
Revision History
Revision | Description | Author | Issue Date
V1.0 | Module Manage News & Manage FAQ | Khoi Nguyen | 14/05/2017
V1.1 | Module Manage Accounts + Manage Categories + Manage Banners | Minh Doan | 15/05/2017
PRODUCT APPROVAL PROCESS - Customers will declare approved in writing if the specifications have been successfully implemented and all requirements under Article 3. Acceptable product standards have been followed. If not, customers will deny in a written report. - Customer will provide software development team the necessary time and opportunity to correct the error occurred. If measures are not able to fix, or is not reasonable, the development team is committed to providing solutions for intermediate to solve the error. The procedure is repeated until all the fix mentioned in the error text.

## UAT-Release 1
ID | Module | Function | Conditions of approval | Accept | Refuse
1 | Manage News | View News | Website have to show news for user
2 |  |  | CMS page have to show news for Content Admin/Education staff
3 |  |  | CMS page have to show news for Editor
4 |  | View Drafts | CMS page have to show drafts for Content Admin/Education staff
5 |  |  | CMS page have to show drafts for Editor
6 |  | Create Drafts | CMS page have to show form create draft for Content Admin/Education Staff include : - Title - Brief content - Content ( can insert image )
7 |  |  | CMS page have to show form create draft for Editor include : - Title - Brief content Content ( can insert image )
8 |  | Edit Drafts | CMS page have to show form edit draft for Content Admin/Education Staff include : - Title - Brief content - Content ( can insert image )
9 |  |  | CMS page have to show form edit draft for Content Admin/Education Staff include : - Title - Brief content - Content ( can insert image )
10 |  | Delete Drafts | Content Admin/Education Staff can delete drafts
11 |  |  | Editor can delete drafts
12 |  | Transfer Drafts | Content Admin/Education Staff can choose Editor & transfer drafts
13 |  |  | Editor can transfer drafts to Content Admin
14 |  | Approve Drafts | Content Admin can approve drafts from Editor transfer
15 |  | Post News | Content Admin can post news approved on website
16 |  | Deactive News | Content Admin can deactivate news posted
17 |  | Search News | User can search news which they want to view in website
18 |  |  | Content Admin/Education Staff can search news which they want to view in website
19 |  |  | Editor can search news which they want to view in website
20 |  | Push News | Content Admin can push news approved on top of news area at homepage
21 |  | Share News | User can share news to Social Network ( Facebook , Twitter , Google+ … )
22 | Manage Accounts | Login | System have to show CMS page of Content Admin
23 |  |  | System have to show CMS page of System Admin
24 |  |  | System have to show CMS page of Editor/Education Staff
25 |  | Logout | System have to show Login page
26 |  | Create Account | System Admin can create new account
27 |  | Edit Account | System Admin can edit information of the existing account
28 |  | Search Account | System show account which the same as key search in the CMS page
29 |  | Forget Password | System show success message and send new Password to email
30 |  | View Profile of Account | User can view form profile of this account
31 |  | View List of Account | System Admin can view list of account in CMS page
32 |  | Authorize | System Admin can authorize for account in the list of account
33 |  | Deactive Account | System Admin can deactivate account
34 |  | Active Account | System Admin can activate account
35 | Manage Categories | View Categories in Homepage | System show the category in homepage
36 |  | View Categories in CMS | Content Admin/Education Staff/Editor can view the list of categories in CMS page
37 |  | Add Category | Content Admin can add new category
38 |  | Edit Category | Content Admin can edit information of category
39 |  | Delete Category | Content Admin can delete the existing category

## UAT-Release 2
ID | Module | Function | Conditions of approval | Accept | Refuse
1 | Manage FAQ | Send Question | User can send question successfully with Send question form include : - Fullname - Email - Question
2 |  | Answer Question | Content Admin/Education Staff/Editor can send answer via email of user Answer form include : - To (who) - Answer
3 |  | View Question | Website have to show frequently asked questions for user
4 |  |  | CMS page have to show all question of student for Content Admin/Editor/Education Staff
5 |  | Approve Question | Content Admin can approve the common question answered into website
6 |  | Search Question | User can search question which they want to view in website
7 | Manage Banners | Create Banner | Content Admin can add new banner
8 |  | View Banner | System have to show banner in the homepage
9 |  |  | System have to show list of banner in CMS page
10 |  | Edit Banner | Content Admin can edit information of banner
11 |  | Delete Banner | Content Admin can delete the existing banner in list of banner
12 |  | Show/Hide Banner | Content Admin can show/hide banner
13 |  | Arrange Banners | Content Admin can arrange banners, and system have to show banner follow the order of banner

## UAT-Release 3
ID | Module | Function | Conditions of approval | Accept | Refuse
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20