## Report
WEEKLY REPORT
WEEK: 25
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 20/3/2017 | 20/3/2017 | HaiTran | 2 | 2
2 | Implement "Import score" function | 20/3/2017 | 22/3/2017 |  | 26 | 26
3 | Training Technical | 21/3/2017 | 21/3/2017 |  | 2 | 2
4 | Mentor Meeting | 23/3/2017 | 23/3/2017 |  | 2 | 4
5 | Team Meeting | 20/3/2017 | 20/3/2017 | HienNguyen | 2 | 2
6 | Implement "Import score" function | 20/3/2017 | 22/3/2017 |  | 25 | 26
7 | Training Technical | 21/3/2017 | 21/3/2017 |  | 2 | 2
8 | Mentor Meeting | 23/3/2017 | 23/3/2017 |  | 2 | 4
9 | Mentor Meeting | 23/3/2017 | 23/3/2017 | KhoiNguyen | 2 | 4
10 | Test "News" function | 24/3/2017 | 25/3/2017 |  | 15 | 16
11 | Test "News" function | 24/3/2017 | 25/3/2017 | MinhDoan | 15 | 15
12 | Team Meeting | 20/3/2017 | 20/3/2017 | TaiNguyen | 2 | 2
13 | Implement "Import score" function | 20/3/2017 | 22/3/2017 |  | 25 | 26
14 | Training Technical | 21/3/2017 | 21/3/2017 |  | 2 | 2
15 | Mentor Meeting | 23/3/2017 | 23/3/2017 |  | 2 | 4
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 32 | 34
|  |  |  | HienNguyen | 31 | 34
|  |  |  | KhoiNguyen | 17 | 20
|  |  |  | MinhDoan | 15 | 15
|  |  |  | TaiNguyen | 31 | 34
|  |  |  | XuanThaiHien | 0 | 0

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time