## Report
WEEKLY REPORT
WEEK: 24
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 27/3/2017 | 27/3/2017 | HaiTran | 2 | 2
2 | Fix "News" function | 27/3/2017 | 28/3/2017 |  | 15 | 14
3 | Training Technical | 28/3/2017 | 28/3/2017 |  | 2 | 2
4 | Implement "Import score" function | 30/3/2017 | 31/3/2017 |  | 16 | 15
5 | Fix "Category" function | 2017-01-04 | 2017-01-04 |  | 8 | 8
6 | Meeting mentor | 2017-01-04 | 2017-01-04 |  | 2 | 3
7 | Team Meeting | 27/3/2017 | 27/3/2017 | HienNguyen | 2 | 2
8 | Fix "News" function | 27/3/2017 | 28/3/2017 |  | 15 | 14
9 | Training Technical | 28/3/2017 | 28/3/2017 |  | 2 | 2
10 | Implement "Import score" function | 30/3/2017 | 31/3/2017 |  | 16 | 15
11 | Fix "Category" function | 2017-01-04 | 2017-01-04 |  | 8 | 7
12 | Meeting mentor | 2017-01-04 | 2017-01-04 |  | 2 | 3
13 | Re-test "News" function | 28/3/2017 | 28/3/2017 | KhoiNguyen | 7 | 6
14 | Create unit test for "Category" function | 29/3/2017 | 30/3/2017 |  | 18 | 16
15 | Test "Category" function | 2017-01-04 | 2017-01-04 |  | 8 | 7
16 | Meeting mentor | 2017-01-04 | 2017-01-04 |  | 2 | 3
17 | Re-test "News" function | 28/3/2017 | 28/3/2017 | MinhDoan | 6 | 6
18 | Create unit test for "Category" function | 29/3/2017 | 30/3/2017 |  | 17 | 16
19 | Test "Category" function | 2017-01-04 | 2017-01-04 |  | 7 | 7
20 | Meeting mentor | 2017-01-04 | 2017-01-04 |  | 2 | 3
21 | Team Meeting | 27/3/2017 | 27/3/2017 | TaiNguyen | 2 | 2
22 | Fix "News" function | 27/3/2017 | 28/3/2017 |  | 15 | 14
23 | Training Technical | 28/3/2017 | 28/3/2017 |  | 2 | 2
24 | Implement "Import score" function | 30/3/2017 | 31/3/2017 |  | 15 | 15
25 | Fix "Category" function | 2017-01-04 | 2017-01-04 |  | 8 | 7
26 | Meeting mentor | 2017-01-04 | 2017-01-04 |  | 2 | 3
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 45 | 44
|  |  |  | HienNguyen | 45 | 43
|  |  |  | KhoiNguyen | 35 | 32
|  |  |  | MinhDoan | 32 | 32
|  |  |  | TaiNguyen | 44 | 43
|  |  |  | XuanThaiHien | 0 | 0

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time