## Report
WEEKLY REPORT
WEEK: 27
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 2017-03-04 | 2017-03-04 | HaiTran | 2 | 2
2 | Training Technical | 2017-04-04 | 2017-04-04 |  | 2 | 2
3 | Implement "FAQ" function on front-end | 2017-05-04 | 2017-06-04 |  | 17 | 18
4 | Fix "Account" function | 2017-07-04 | 2017-07-04 |  | 6 | 6
5 | Meeting mentor | 2017-08-04 | 2017-08-04 |  | 2 | 3
6 | Team Meeting | 2017-03-04 | 2017-03-04 | HienNguyen | 2 | 2
7 | Training Technical | 2017-04-04 | 2017-04-04 |  | 2 | 2
8 | Implement "FAQ" function on server | 2017-05-04 | 2017-06-04 |  | 18 | 18
9 | Fix "Account" function | 2017-07-04 | 2017-07-04 |  | 6 | 6
10 | Meeting mentor | 2017-08-04 | 2017-08-04 |  | 2 | 3
11 | Re-test "Category" function | 2017-03-04 | 2017-03-04 | KhoiNguyen | 7 | 7
12 | Create unit test "Account" function | 2017-04-04 | 2017-04-04 |  | 8 | 7
13 | Test "Account" function | 2017-06-04 | 2017-06-04 |  | 6 | 7
14 | Meeting mentor | 2017-08-04 | 2017-08-04 |  | 2 | 3
15 | Re-test "Category" function | 2017-03-04 | 2017-03-04 | MinhDoan | 6 | 7
16 | Create unit test "Account" function | 2017-04-04 | 2017-04-04 |  | 8 | 6
17 | Test "Account" function | 2017-06-04 | 2017-06-04 |  | 7 | 7
18 | Meeting mentor | 2017-08-04 | 2017-08-04 |  | 2 | 3
19 | Team Meeting | 2017-03-04 | 2017-03-04 | TaiNguyen | 2 | 2
20 | Training Technical | 2017-04-04 | 2017-04-04 |  | 2 | 2
21 | Implement "FAQ" function on CMS | 2017-05-04 | 2017-06-04 |  | 17 | 18
22 | Fix "Account" function | 2017-07-04 | 2017-07-04 |  | 5 | 6
23 | Meeting mentor | 2017-08-04 | 2017-08-04 |  | 2 | 3
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 29 | 31
|  |  |  | HienNguyen | 30 | 31
|  |  |  | KhoiNguyen | 23 | 24
|  |  |  | MinhDoan | 23 | 23
|  |  |  | TaiNguyen | 28 | 31
|  |  |  | XuanThaiHien | 0 | 0

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time