## Report
WEEKLY REPORT
WEEK: 28
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 2017-10-04 | 2017-10-04 | HaiTran | 2 | 2
2 | Training Technical | 2017-11-04 | 2017-11-04 |  | 2 | 2
3 | Fix "Banner" function | 13/4/2017 | 13/4/2017 |  | 7 | 7
4 | Mentor Meeting | 15/4/2017 | 15/4/2017 |  | 2 | 3
5 | Team Meeting | 2017-10-04 | 2017-10-04 | HienNguyen | 2 | 2
6 | Training Technical | 2017-11-04 | 2017-11-04 |  | 2 | 2
7 | Fix "Banner" function | 13/4/2017 | 13/4/2017 |  | 6 | 8
8 | Mentor Meeting | 15/4/2017 | 15/4/2017 |  | 2 | 3
9 | Create unit test "Banner" function | 2017-10-04 | 2017-11-04 | KhoiNguyen | 8 | 7
10 | Re-test "Account" function | 2017-11-04 | 2017-11-04 |  | 3 | 3
11 | Test "Banner" function | 2017-12-04 | 2017-12-04 |  | 7 | 7
12 | Create unit test "Import score" function | 14/4/2017 | 14/4/2017 |  | 6 | 5
13 | Re-test "Banner" function | 15/4/2017 | 15/4/2017 |  | 4 | 5
14 | Mentor Meeting | 15/4/2017 | 15/4/2017 |  | 2 | 3
15 | Create unit test "Banner" function | 2017-10-04 | 2017-11-04 | MinhDoan | 7 | 7
16 | Re-test "Account" function | 2017-11-04 | 2017-11-04 |  | 3 | 4
17 | Test "Banner" function | 2017-12-04 | 2017-12-04 |  | 6 | 7
18 | Create unit test "Import score" function | 14/4/2017 | 14/4/2017 |  | 6 | 6
19 | Team Meeting | 2017-10-04 | 2017-10-04 | TaiNguyen | 2 | 2
20 | Training Technical | 2017-11-04 | 2017-11-04 |  | 2 | 2
21 | Fix "Banner" function | 13/4/2017 | 13/4/2017 |  | 6 | 7
22 | Mentor Meeting | 15/4/2017 | 15/4/2017 |  | 2 | 3
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 13 | 14
|  |  |  | HienNguyen | 12 | 15
|  |  |  | KhoiNguyen | 30 | 30
|  |  |  | MinhDoan | 22 | 24
|  |  |  | TaiNguyen | 12 | 14
|  |  |  | XuanThaiHien | 0 | 0

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time