## Report
WEEKLY REPORT
WEEK: 29
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 17/4/2017 | 17/4/2017 | HaiTran | 2 | 2
2 | Training Technical | 18/4/2017 | 18/4/2017 |  | 2 | 2
3 | Customer Meeting | 19/4/2017 | 19/4/2017 |  | 2 | 2
4 | Design UX | 19/4/2017 | 19/4/2017 |  | 6 | 6
5 | Mentor Meeting | 20/4/2017 | 20/4/2017 |  | 2 | 2
6 | Modify "Planning" document | 20/4/2017 | 20/4/2017 |  | 5 | 4
7 | Mentor Meeting | 22/4/2017 | 22/4/2017 |  | 2 | 3
8 | Fix "FAQ" function | 22/4/2017 | 22/4/2017 |  | 5 | 6
9 | Team Meeting | 13/3/2017 | 17/4/2017 | HienNguyen | 2 | 2
10 | Fix " Import score" function | 13/3/2017 | 18/4/2017 |  | 7 | 8
11 | Training Technical | 14/3/2017 | 18/4/2017 |  | 2 | 2
12 | Customer Meeting | 14/3/2017 | 19/4/2017 |  | 2 | 2
13 | Mentor Meeting | 15/3/2017 | 20/4/2017 |  | 2 | 2
14 | Mentor Meeting | 17/3/2017 | 22/4/2017 |  | 2 | 3
15 | Fix "FAQ" function | 18/3/2017 | 22/4/2017 |  | 5 | 6
16 | Test "Import score" function | 17/4/2017 | 17/4/2017 | KhoiNguyen | 5 | 6
17 | Re-test "Import score" function | 18/4/2017 | 18/4/2017 |  | 5 | 6
18 | Customer Meeting | 19/4/2017 | 19/4/2017 |  | 2 | 2
19 | Mentor Meeting | 20/4/2017 | 20/4/2017 |  | 2 | 2
20 | Create unit test "FAQ" function | 21/4/2017 | 21/4/2017 |  | 6 | 7
21 | Mentor Meeting | 22/4/2017 | 22/4/2017 |  | 2 | 3
22 | Test "FAQ" funtion | 22/4/2017 | 22/4/2017 |  | 4 | 5
23 | Test "Import score" function | 17/4/2017 | 17/4/2017 | MinhDoan | 6 | 6
24 | Modify "Requirement" document | 20/4/2017 | 20/4/2017 |  | 5 | 6
25 | Create unit test "FAQ" function | 21/4/2017 | 21/4/2017 |  | 7 | 7
26 | Test "FAQ" funtion | 22/4/2017 | 22/4/2017 |  | 5 | 5
27 | Team Meeting | 17/4/2017 | 17/4/2017 | TaiNguyen | 2 | 2
28 | Fix " Import score" function | 17/4/2017 | 18/4/2017 |  | 7 | 7
29 | Training Technical | 18/4/2017 | 18/4/2017 |  | 2 | 2
30 | Customer Meeting | 19/4/2017 | 19/4/2017 |  | 2 | 2
31 | Design UX | 19/4/2017 | 19/4/2017 |  | 5 | 6
32 | Mentor Meeting | 20/4/2017 | 20/4/2017 |  | 2 | 2
33 | Mentor Meeting | 22/4/2017 | 22/4/2017 |  | 2 | 3
34 | Fix "FAQ" function | 22/4/2017 | 22/4/2017 |  | 6 | 6
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 26 | 27
|  |  |  | HienNguyen | 22 | 25
|  |  |  | KhoiNguyen | 26 | 31
|  |  |  | MinhDoan | 23 | 24
|  |  |  | TaiNguyen | 28 | 30
|  |  |  | XuanThaiHien | 0 | 0

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time