## Report
WEEKLY REPORT
WEEK: 30
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 24/4/2017 | 24/4/2017 | HaiTran | 2 | 2
2 | Technical training | 25/4/2017 | 25/4/2017 |  | 2 | 2
3 | Integrate project to host server | 25/4/2017 | 25/4/2017 |  | 4 | 4
4 | Fix release 1 | 26/4/2017 | 26/4/2017 |  | 3 | 3
5 | Mentor Meeting | 28/4/2017 | 28/4/2017 |  | 3 | 2
6 | Team Meeting | 24/4/2017 | 24/4/2017 | HienNguyen | 2 | 2
7 | Technical training | 25/4/2017 | 25/4/2017 |  | 2 | 2
8 | Integrate project to host server | 25/4/2017 | 25/4/2017 |  | 4 | 4
9 | Fix release 1 | 26/4/2017 | 26/4/2017 |  | 3 | 3
10 | Mentor Meeting | 28/4/2017 | 28/4/2017 |  | 3 | 2
11 | Team Meeting | 24/4/2017 | 24/4/2017 | KhoiNguyen | 2 | 2
12 | Re-test "FAQ" function | 24/4/2017 | 24/4/2017 |  | 5 | 4
13 | Test release 1 | 25/4/2017 | 26/4/2017 |  | 8 | 7
14 | Re-test release 1 | 27/4/2017 | 27/4/2017 |  | 3 | 2
15 | Mentor Meeting | 28/4/2017 | 28/4/2017 |  | 3 | 2
16 | Report test release 1 | 29/4/2017 | 29/4/2017 |  | 3 | 3
17 | Team Meeting | 24/4/2017 | 24/4/2017 | MinhDoan | 2 | 2
18 | Re-test "FAQ" function | 24/4/2017 | 24/4/2017 |  | 5 | 5
19 | Test release 1 | 25/4/2017 | 26/4/2017 |  | 9 | 8
20 | Re-test release 1 | 27/4/2017 | 27/4/2017 |  | 3 | 2
21 | Mentor Meeting | 28/4/2017 | 28/4/2017 |  | 3 | 2
22 | Report test release 1 | 29/4/2017 | 29/4/2017 |  | 3 | 3
23 | Team Meeting | 24/4/2017 | 24/4/2017 | TaiNguyen | 2 | 2
24 | Technical training | 25/4/2017 | 25/4/2017 |  | 2 | 2
25 | Integrate project to host server | 25/4/2017 | 25/4/2017 |  | 4 | 4
26 | Fix release 1 | 26/4/2017 | 26/4/2017 |  | 4 | 3
27 | Mentor Meeting | 28/4/2017 | 28/4/2017 |  | 3 | 2
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 14 | 13
|  |  |  | HienNguyen | 14 | 13
|  |  |  | KhoiNguyen | 24 | 20
|  |  |  | MinhDoan | 25 | 22
|  |  |  | TaiNguyen | 15 | 13
|  |  |  | XuanThaiHien | 0 | 0

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time