## Report
WEEKLY REPORT
WEEK: 31
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 2017-03-05 | 2017-03-05 | HaiTran | 2 | 2
2 | Fix release 2 | 2017-03-05 | 2017-04-05 |  | 5 | 5
3 | Mentor Meeting | 2017-05-05 | 2017-05-05 |  | 3 | 3
4 | Team Meeting | 2017-03-05 | 2017-03-05 | HienNguyen | 2 | 2
5 | Fix release 2 | 2017-03-05 | 2017-04-05 |  | 6 | 5
6 | Mentor Meeting | 2017-05-05 | 2017-05-05 |  | 3 | 3
7 | Team Meeting | 2017-03-05 | 2017-03-05 | KhoiNguyen | 2 | 2
8 | Test release 2 | 2017-03-05 | 2017-04-05 |  | 4 | 5
9 | Mentor Meeting | 2017-05-05 | 2017-05-05 |  | 3 | 3
10 | Re-test release 2 | 2017-05-05 | 2017-05-05 |  | 3 | 3
11 | Report test release 2 | 2017-06-05 | 2017-06-05 |  | 4 | 2
12 | Team Meeting | 2017-03-05 | 2017-03-05 | MinhDoan | 2 | 2
13 | Test release 2 | 2017-03-05 | 2017-04-05 |  | 4 | 3
14 | Mentor Meeting | 2017-05-05 | 2017-05-05 |  | 3 | 3
15 | Re-test release 2 | 2017-05-05 | 2017-05-05 |  | 3 | 3
16 | Report test release 2 | 2017-06-05 | 2017-06-05 |  | 4 | 2
17 | Team Meeting | 2017-03-05 | 2017-03-05 | TaiNguyen | 2 | 2
18 | Fix release 2 | 2017-03-05 | 2017-04-05 |  | 6 | 5
19 | Mentor Meeting | 2017-05-05 | 2017-05-05 |  | 3 | 3
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 10 | 10
|  |  |  | HienNguyen | 11 | 10
|  |  |  | KhoiNguyen | 16 | 15
|  |  |  | MinhDoan | 16 | 13
|  |  |  | TaiNguyen | 11 | 10
|  |  |  | XuanThaiHien | 0 | 0

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time