## Report
WEEKLY REPORT
WEEK: 33
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 15/5/2017 | 15/5/2017 | HaiTran | 2 | 2
2 | Change image server on editor | 15/5/2017 | 16/5/2017 |  | 11 | 10
3 | Modify "Architecture and design" document-dynamic view level 2 | 17/5/2017 | 18/5/2017 |  | 14 | 14
4 | Mentor Meeting | 19/5/2017 | 19/5/2017 |  | 2 | 2
5 | Technical training | 19/5/2017 | 19/5/2017 |  | 2 | 2
6 | Modify "Detail design" document | 19/5/2017 | 20/5/2017 |  | 9 | 7
7 | Team Meeting | 15/5/2017 | 15/5/2017 | HienNguyen | 2 | 2
8 | Change image server on editor | 15/5/2017 | 16/5/2017 |  | 11 | 10
9 | Modify "Architecture and design" document-physical view | 17/5/2017 | 14/3/2017 |  | 12 | 13
10 | Mentor Meeting | 19/5/2017 | 19/5/2017 |  | 2 | 2
11 | Technical training | 19/5/2017 | 19/5/2017 |  | 2 | 2
12 | Modify "Detail design" document | 19/5/2017 | 20/5/2017 |  | 8 | 8
13 | Team Meeting | 15/5/2017 | 15/5/2017 | KhoiNguyen | 2 | 2
14 | Test release 1 | 16/5/2017 | 16/5/2017 |  | 5 | 6
15 | Report test release 1 | 17/5/2017 | 17/5/2017 |  | 3 | 2
16 | Modify "Architecture and design" document-static view level 2 | 17/5/2017 | 18/5/2017 |  | 13 | 14
17 | Mentor Meeting | 19/5/2017 | 19/5/2017 |  | 2 | 2
18 | Modify "Detail design" document | 19/5/2017 | 20/5/2017 |  | 8 | 7
19 | Team Meeting | 15/5/2017 | 15/5/2017 | MinhDoan | 2 | 2
20 | Test release 1 | 16/5/2017 | 16/5/2017 |  | 6 | 6
21 | Report test release 1 | 17/5/2017 | 17/5/2017 |  | 3 | 2
22 | Modify "Architecture and design" document-static view level 1 | 17/5/2017 | 18/5/2017 |  | 12 | 14
23 | Mentor Meeting | 19/5/2017 | 19/5/2017 |  | 2 | 2
24 | Modify "Detail design" document | 19/5/2017 | 20/5/2017 |  | 9 | 8
25 | Team Meeting | 15/5/2017 | 15/5/2017 | TaiNguyen | 2 | 2
26 | Change image server on editor | 15/5/2017 | 16/5/2017 |  | 10 | 10
27 | Modify "Architecture and design" document-dynamic view level 1 | 17/5/2017 | 18/5/2017 |  | 12 | 12
28 | Mentor Meeting | 19/5/2017 | 19/5/2017 |  | 2 | 2
29 | Technical training | 19/5/2017 | 19/5/2017 |  | 2 | 2
30 | Modify "Detail design" document | 19/5/2017 | 20/5/2017 |  | 8 | 8
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 40 | 37
|  |  |  | HienNguyen | 37 | 33
|  |  |  | KhoiNguyen | 33 | 33
|  |  |  | MinhDoan | 34 | 34
|  |  |  | TaiNguyen | 36 | 36
|  |  |  | XuanThaiHien | 0 | 0

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time