## Report
WEEKLY REPORT
WEEK: 24
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 13/3/2017 | 13/3/2017 | HaiTran | 2 | 2
2 | Implement "Arrange Banner" function on server | 13/3/2017 | 14/3/2017 |  | 15 | 16
3 | Training Technical | 14/3/2017 | 14/3/2017 |  | 2 | 2
4 | Implement "Create Popups" function on server | 14/3/2017 | 15/3/2017 |  | 14 | 12
5 | Implement "Arrange Popups" function on server | 15/3/2017 | 16/3/2017 |  | 15 | 14
6 | Research publish code to server | 17/3/2017 | 17/3/2017 |  | 7 | 8
7 | Mentor Meeting | 18/3/2017 | 18/3/2017 |  | 2 | 3
8 | Team Meeting | 13/3/2017 | 13/3/2017 | HienNguyen | 2 | 2
9 | Implement "Arrange Banner" function on server | 13/3/2017 | 14/3/2017 |  | 16 | 18
10 | Training Technical | 14/3/2017 | 14/3/2017 |  | 2 | 2
11 | Implement "Create Popups" function on server | 14/3/2017 | 15/3/2017 |  | 14 | 12
12 | Implement "Arrange Popups" function on server | 15/3/2017 | 16/3/2017 |  | 16 | 14
13 | Research publish code to server | 17/3/2017 | 17/3/2017 |  | 7 | 8
14 | Mentor Meeting | 18/3/2017 | 18/3/2017 |  | 2 | 3
15 | Team Meeting | 13/3/2017 | 13/3/2017 | KhoiNguyen | 2 | 2
16 | Training Technical | 14/3/2017 | 14/3/2017 |  | 2 | 2
17 | Create unit test for "News" function | 17/3/2017 | 17/3/2017 |  | 9 | 7
18 | Mentor Meeting | 18/3/2017 | 18/3/2017 |  | 2 | 3
19 | Team Meeting | 13/3/2017 | 13/3/2017 | MinhDoan | 2 | 2
20 | Training Technical | 14/3/2017 | 14/3/2017 |  | 2 | 2
21 | Create unit test for "News" function | 17/3/2017 | 17/3/2017 |  | 8 | 7
22 | Mentor Meeting | 18/3/2017 | 18/3/2017 |  | 2 | 3
23 | Team Meeting | 13/3/2017 | 13/3/2017 | TaiNguyen | 2 | 2
24 | Implement "Arrange Banner" function on frontend | 13/3/2017 | 14/3/2017 |  | 14 | 15
25 | Training Technical | 14/3/2017 | 14/3/2017 |  | 2 | 2
26 | Implement "Create Popups" function on frontend | 14/3/2017 | 15/3/2017 |  | 12 | 12
27 | Implement "Arrange Popups" function on frontend | 15/3/2017 | 16/3/2017 |  | 12 | 15
28 | Research publish code to server | 17/3/2017 | 17/3/2017 |  | 7 | 8
29 | Mentor Meeting | 18/3/2017 | 18/3/2017 |  | 2 | 3
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 57 | 57
|  |  |  | HienNguyen | 59 | 59
|  |  |  | KhoiNguyen | 15 | 14
|  |  |  | MinhDoan | 14 | 14
|  |  |  | TaiNguyen | 51 | 57
|  |  |  | XuanThaiHien | 0 | 0

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time