## Slide 1: EOMP #2
Mentor: Vu The Nam
Team: Base Steps Solution
Project: Van Lang Admission

## Slide 2: Objective
Give what we have achieved in recent time
Current progress report
Given the problems that occurred in team and the lessons learned

## Slide 3: Outline
Introduction project
Requirement
Architecture
Progress of project
Risk and issue report
Reflection

## Slide 4: Introduction project

## Slide 5: Base Steps Solution
Mentor: Vu The Nam
Members:
  Nguyen Thai Hien
  Tran Xuan Hai
  Nguyen Hoang Anh Tai
  Nguyen Anh Khoi
  Doan Anh Minh
  Nguyen Xuan Thai Hien

## Slide 6: Project overview
Project name: Van Lang admission
Customer: Van Lang university
Goals:
  Create a website Van Lang Admission for customer with high quality & the most reasonable price
  Website can work with the best performance and take this site close to all student in Viet Nam
  Website can help introduce all information and make a good look for Van Lang university
  Website can help students lookup their admission information correctly & clearly

## Slide 7: Software development process

## Slide 8: Requirement

## Slide 9: Requirement process

## Slide 10: Quality attribute
Id | Quality Attribute | Description | Priority
SQA-P01 | Performance | When users use the system to view the necessary information, the system will respond quickly, display results in 2 seconds | High
SQA-P02 |  | Education staffs can import point into system average 1000 points will import about 4 seconds | High
SQA-A01 | Availability | When Web server unresponsive, can re-operation quickly | High
SQA-C01 | Scalability | System can expand limit number of users | High
SQA-U01 | Usability | System has friendly interface and easy to use | Medium
SQA-R01 | Portability | Users can use the system on mobile platform | Medium
SQA-M01 | Modifiability | The system can add/delete/modify other functions later | Medium
SQA-S01 | Security | System can authorize user’s information | Low

## Slide 11: Architecture

## Slide 12: Architect process

## Slide 13: Physical view

## Slide 14: Dynamic view

## Slide 15: Static view

## Slide 16: Progress of project

## Slide 17
Chart: Earned value chart
| W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36
BCWS | 61.28 | 95.408 | 240.2113 | 392.038 | 650.078 | 704.678 | 787.3247 | 1047.3247 | 1157.028 | 1469.328 | 1556.0347 | 1656.9347 | 1773.3547 | 2090.3547 | 2221.3547 | 2352.3547 | 2498.3547 | 2498.3547 | 2574.3547 | 2663.3547 | 2927.9213 | 3174.8147 | 3288.6013 | 3461.248 | 3670.3813 | 3830.2547 | 3984.0547 | 4111.548 | 4263.1013 | 4468.5947
BCWP | 61.26 | 95.26 | 181.11 | 307.283 | 481.116 | 588.243 | 679.93 | 858.25 | 936.407 | 1013.654 | 1153.357 | 1309.95 | 1497.517 | 1544.2177 | 1610.1177 | 1676.5377 | 1800.6377 | 1800.6377 | 1946.8307 | 2241.8307
ACWP | 87 | 172 | 294 | 407 | 609 | 732 | 859 | 994 | 1169 | 1349 | 1513 | 1684 | 1887 | 2068.15 | 2158.15 | 2377.15 | 2578.15 | 2578.15 | 2790.15 | 2979.15 | 3179.15 | 3379.15 | 3579.15 | 3779.15 | 3979.15 | 4179.15 | 4379.15 | 4579.15 | 4779.15 | 4979.15 | 5179.15 | 5379.15 | 5579.15 | 5779.15 | 5879.15 | 5938.278

## Slide 18
Chart: Schedule & Cost Index Trends
| 0.99967362924281977 | 0.99844876739896016 | 0.75396109536880118 | 0.78380922257536256 | 0.74008965078036792 | 0.83476850419624271 | 0.86359545024627704 | 0.81946890712653897 | 0.80932094988193892 | 0.68987591606503107 | 0.74121549134295206 | 0.79058639206051973 | 0.84445431483531019 | 0.73873476669987737 | 0.7248359260955477 | 0.71270616236440532 | 0.72072940284432518 | 0.72072940284432518 | 0.75624026953551071 | 0.84173193118352985
 | 0.70414 | 0.55384 | 0.61602 | 0.755 | 0.79001 | 0.80361 | 0.79154 | 0.86343 | 0.80103 | 0.75141 | 0.7623 | 0.77788 | 0.7936 | 0.74667 | 0.74606 | 0.70527 | 0.69842 | 0.69842 | 0.69775 | 0.75251

## Slide 19: Risk and issue report

## Slide 20: Risk management process

## Slide 21
Chart: Risk Priority
| High | Medium | Low
 | 9 | 10 | 4
Chart: Risk status
| New | Planned | In Progress | Closed | Reject
 | 0 | 7 | 5 | 4 | 7
Chart: Risk department
| Planning | Management | Requirement | Architect | Desgin | Code | Test
 | 1 | 7 | 10 | 2 | 2 | 1 | 0
Chart: Issue Status
| Active | Fixed
 | 5 | 4

## Slide 22: Reflection

## Slide 23
ID | Issue | Solution | Actual Status | Result | Lession Learned
1 | Estimates are inaccurate | Team meeting and re-estimate. | Active | N/A | - Need to learn the method of estimating - Estimating together
2 | Lack of needed knowledge | Research and increase effort to study new programming language. | Active | N/A | - Need to prepare the study materials at beginning - Need regular practice
3 | Resources are inexperienced | All member research and read documents of previous course. | Fixed | Team members found a number of documents on the network & previous course | - Need to prepare the study materials from the beginning
4 | Errors in key project management processes | Team meeting to review each key process and modify them. | Fixed | Modify all document templates Synchronize all processes | - Modify all document templates at beginning - Draw process with one configuration
5 | Team members with negative attitudes towards the project | Team meeting to solve the problem. | Fixed | Have some team building to improve motivation of team work Team focused and eager to work together | - Member of team should respect each other - Prioritize work on top
6 | Inaccurate function priorities | Review with customer to define clearly for function priorities. | Fixed | Reviewed priorities of all function | - Need understand clearly about requirement of customer
7 | Architecture is infeasible | Research and collect advices from professor | Active | N/A | - Need to learn the method of estimating - Build base on Quality Attributes
8 | Delays to training impact the project | Increase effort for all members. | Active | N/A | - Need to trainning at beginning
9 | Customer rejects the prototype | Request some prototypes of others website to customer, re-design follow the choice of customer. | Active | N/A | - Need understand clearly about requirement of customer

## Slide 24: Thank for your attention!