## Sheet1
|  | Project Lead: | Hai Tran
|  | Project Start Date: | 2016-10-03 | time axis 2016-10-03 to 2017-04-30
|  | Display Week: | 1 |  |  | 2016-10-03: Week 1; 2016-10-10: Week 2; 2016-10-17: Week 3; 2016-10-24: Week 4; 2016-10-31: Week 5; 2016-11-07: Week 6; 2016-11-14: Week 7; 2016-11-21: Week 8; 2016-11-28: Week 9; 2016-12-05: Week 10; 2016-12-12: Week 11; 2016-12-19: Week 12; 2016-12-26: Week 13; 2017-01-02: Week 14; 2017-01-09: Week 15; 2017-01-16: Week 16; 2017-01-23: Week 17; 2017-01-30: Week 18; 2017-02-06: Week 19; 2017-02-13: Week 20; 2017-02-20: Week 21; 2017-02-27: Week 22; 2017-03-06: Week 23; 2017-03-13: Week 24; 2017-03-20: Week 25; 2017-03-27: Week 26; 2017-04-03: Week 27; 2017-04-10: Week 28; 2017-04-17: Week 29; 2017-04-24: Week 30
[6 empty] | 2016-10-03 | [6 empty] | 2016-10-10 | [6 empty] | 2016-10-17 | [6 empty] | 2016-10-24 | [6 empty] | 2016-10-31 | [6 empty] | 2016-11-07 | [6 empty] | 2016-11-14 | [6 empty] | 2016-11-21 | [6 empty] | 2016-11-28 | [6 empty] | 2016-12-05 | [6 empty] | 2016-12-12 | [6 empty] | 2016-12-19 | [6 empty] | 2016-12-26 | [6 empty] | 2017-01-02 | [6 empty] | 2017-01-09 | [6 empty] | 2017-01-16 | [6 empty] | 2017-01-23 | [6 empty] | 2017-01-30 | [6 empty] | 2017-02-06 | [6 empty] | 2017-02-13 | [6 empty] | 2017-02-20 | [6 empty] | 2017-02-27 | [6 empty] | 2017-03-06 | [6 empty] | 2017-03-13 | [6 empty] | 2017-03-20 | [6 empty] | 2017-03-27 | [6 empty] | 2017-04-03 | [6 empty] | 2017-04-10 | [6 empty] | 2017-04-17 | [6 empty] | 2017-04-24
ID | Task | Task | Start | End | Duration | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
1 | KICK-OFF | KICK-OFF | 2016-10-03 | 2016-10-16 | 14 | bar: 2016-10-03 to 2016-10-16
1.1 |  | Team Meeting | 2016-10-03 | 2016-10-03 | 1
1.2 |  | Develop Team rule & policy | 2016-10-04 | 2016-10-05 | 2
1.3 |  | Develop Team Charter | 2016-10-05 | 2016-10-06 | 2
1.4 |  | Mentor Meeting | 2016-10-07 | 2016-10-07 | 1
1.5 |  | Team Meeting | 2016-10-10 | 2016-10-10 | 1
1.6 |  | Develop Project Charter | 2016-10-11 | 2016-10-12 | 2
1.7 |  | Develop Process Decision | 2016-10-12 | 2016-10-13 | 2
1.8 |  | Mentor Meeting | 2016-10-14 | 2016-10-14 | 1
2 | PLANNING | PLANNING | 2016-10-17 | 2016-11-06 | 21 | bar: 2016-10-17 to 2016-11-06
2.1 |  | Team Meeting | 2016-10-17 | 2016-10-17 | 1
2.2 |  | Define Template | 2016-10-18 | 2016-10-20 | 3
2.3 |  | Mentor Meeting | 2016-10-21 | 2016-10-21 | 1
2.4 |  | Team Meeting | 2016-10-24 | 2016-10-24 | 1
2.5 |  | Training Technical | 2016-10-25 | 2016-10-25 | 1
2.6 |  | Develop Work Break Down Structure | 2016-10-25 | 2016-10-25 | 1
2.7 |  | Develop Requirement Plan | 2016-10-25 | 2016-10-25 | 1
2.8 |  | Develop Implement Plan | 2016-10-26 | 2016-10-26 | 1
2.9 |  | Develop Architecture and Design | 2016-10-26 | 2016-10-26 | 1
2.10 |  | Develop Configuration Plan | 2016-10-27 | 2016-10-27 | 1
2.11 |  | Develop Test Plan | 2016-10-27 | 2016-10-27 | 1
2.12 |  | Mentor Meeting | 2016-10-28 | 2016-10-28 | 1
2.13 |  | Team Meeting | 2016-10-31 | 2016-10-31 | 1
2.14 |  | Develop Risk Management | 2016-10-31 | 2016-10-31 | 1
2.15 |  | Develop Change Management | 2016-10-31 | 2016-10-31 | 1
2.16 |  | Training Technical | 2016-11-01 | 2016-11-01 | 1
2.17 |  | Develop Development Process | 2016-11-01 | 2016-11-01 | 1
2.18 |  | Develop Measurement Process | 2016-11-01 | 2016-11-01 | 1
2.19 |  | Develop Schedule | 2016-11-02 | 2016-11-02 | 1
2.20 |  | Develop Estimation | 2016-11-02 | 2016-11-02 | 1
2.21 |  | Develop Training Plan | 2016-11-02 | 2016-11-02 | 1
2.22 |  | Develop Master Plan | 2016-11-03 | 2016-11-03 | 1
2.23 |  | Gather Question List | 2016-11-03 | 2016-11-03 | 1
2.24 |  | Develop Function List | 2016-11-04 | 2016-11-04 | 1
2.25 |  | Mentor Meeting | 2016-11-04 | 2016-11-04 | 1
3 | REQUIREMENT | REQUIREMENT | 2016-11-07 | 2016-12-11 | 35 | bar: 2016-11-07 to 2016-12-11
3.1 |  | Team Meeting | 2016-11-07 | 2016-11-07 | 1
3.2 |  | Mentor Meeting | 2016-11-07 | 2016-11-07 | 1
3.3 |  | Customer Meeting | 2016-11-08 | 2016-11-08 | 1
3.4 |  | Training Technical | 2016-11-08 | 2016-11-08 | 1
3.5 |  | Develop Vision and Scope Document | 2016-11-09 | 2016-11-12 | 4
3.6 |  | Team Meeting | 2016-11-14 | 2016-11-14 | 1
3.7 |  | Mentor Meeting | 2016-11-14 | 2016-11-14 | 1
3.8 |  | Training Technical | 2016-11-15 | 2016-11-15 | 1
3.9 |  | Develop Concept of Operation Document | 2016-11-15 | 2016-11-19 | 5
3.10 |  | Team Meeting | 2016-11-21 | 2016-11-21 | 1
3.11 |  | Mentor Meeting | 2016-11-21 | 2016-11-21 | 1
3.12 |  | Customer Meeting | 2016-11-22 | 2016-11-22 | 1
3.13 |  | Training Technical | 2016-11-22 | 2016-11-22 | 1
3.14 |  | Develop URD Document | 2016-11-22 | 2016-11-26 | 5
3.15 |  | Team Meeting | 2016-11-28 | 2016-11-28 | 1 | bar: 2016-11-28
3.16 |  | Mentor Meeting | 2016-11-28 | 2016-11-28 | 1 | bar: 2016-11-28
3.17 |  | Training Technical | 2016-11-29 | 2016-11-29 | 1 | bar: 2016-11-29
3.18 |  | Develop SRS Document | 2016-11-29 | 2016-12-03 | 5 | bar: 2016-11-29 to 2016-12-03
3.19 |  | Team Meeting | 2016-12-05 | 2016-12-05 | 1 | bar: 2016-11-29 to 2016-12-03; 2016-12-05
3.20 |  | Mentor Meeting | 2016-12-05 | 2016-12-05 | 1 | bar: 2016-12-05
3.21 |  | Training Technical | 2016-12-06 | 2016-12-06 | 1 | bar: 2016-12-06
3.22 |  | Develop Functional Testcase | 2016-12-06 | 2016-12-10 | 5 | bar: 2016-12-06 to 2016-12-10
3.23 |  | Develop User Acceptance Test | 2016-12-06 | 2016-12-10 | 5 | bar: 2016-12-06 to 2016-12-10
3.24 |  | Customer Meeting | 2016-12-10 | 2016-12-10 | 1 | bar: 2016-12-10
4 | ARCHITECTURE |  | 2016-12-12 | 2016-01-01 | 21 | bar: 2016-12-12 to 2017-01-01
4.1 |  | Team Meeting | 2016-12-12 | 2016-12-12 | 1 | bar: 2016-12-12
4.2 |  | Mentor Meeting | 2016-12-12 | 2016-12-12 | 1 | bar: 2016-12-12
4.3 |  | Training Technical | 2016-12-13 | 2016-12-13 | 1 | bar: 2016-12-13
4.4 |  | Draw Physical View | 2016-12-13 | 2016-12-17 | 5 | bar: 2016-12-13 to 2016-12-17
4.5 |  | Team Meeting | 2016-12-19 | 2016-12-19 | 1 | bar: 2016-12-19
4.6 |  | Mentor Meeting | 2016-12-19 | 2016-12-19 | 1 | bar: 2016-12-19
4.7 |  | Training Technical | 2016-12-20 | 2016-12-20 | 1 | bar: 2016-12-20
4.8 |  | Draw Static View | 2016-12-20 | 2016-12-24 | 5 | bar: 2016-12-20 to 2016-12-24
4.9 |  | Team Meeting | 2016-12-26 | 2016-12-26 | 1 | bar: 2016-12-26
4.10 |  | Mentor Meeting | 2016-12-26 | 2016-12-26 | 1 | bar: 2016-12-26
4.11 |  | Training Technical | 2016-12-27 | 2016-12-27 | 1 | bar: 2016-12-27
4.12 |  | Draw Dynamic View | 2016-12-27 | 2016-12-31 | 5 | bar: 2016-12-27 to 2016-12-31
4.13 |  | Customer Meeting | 2016-12-27 | 2016-12-27 | 1 | bar: 2016-12-31
5 | INCREMENTAL 1 | INCREMENTAL 1 | 2017-01-02 | 2017-02-26 | 56 | bar: 2017-01-02 to 2017-01-29; 2017-02-06 to 2017-02-26
5.1 |  | Team Meeting | 2017-01-02 | 2017-01-02 | 1 | bar: 2017-01-02
5.2 |  | Mentor Meeting | 2017-01-02 | 2017-01-02 | 1 | bar: 2017-01-02
5.3 |  | Training Technical | 2017-01-03 | 2017-01-03 | 1 | bar: 2017-01-03
5.4 |  | Draw Class diagram | 2017-01-02 | 2017-01-07 | 6 | bar: 2017-01-02 to 2017-01-07
5.5 |  | Draw Sequence diagram | 2017-01-03 | 2017-01-07 | 5 | bar: 2017-01-03 to 2017-01-07
5.6 |  | Design Database | 2017-01-04 | 2017-01-05 | 2 | bar: 2017-01-04 to 2017-01-05
5.7 |  | Design User Interface | 2017-01-03 | 2017-01-07 | 5 | bar: 2017-01-03 to 2017-01-07
5.8 |  | Team Meeting | 2017-01-09 | 2017-01-09 | 1 | bar: 2017-01-09
5.9 |  | Mentor Meeting | 2017-01-09 | 2017-01-09 | 1 | bar: 2017-01-09
5.10 |  | Training Technical | 2017-01-10 | 2017-01-10 | 1 | bar: 2017-01-10
5.11 |  | Implement "Manage News" function | 2017-01-10 | 2017-01-14 | 5 | bar: 2017-01-10 to 2017-01-14
5.12 |  | Team Meeting | 2017-01-16 | 2017-01-16 | 1 | bar: 2017-01-16
5.13 |  | Mentor Meeting | 2017-01-16 | 2017-01-16 | 1 | bar: 2017-01-16
5.14 |  | Training Technical | 2017-01-17 | 2017-01-17 | 1 | bar: 2017-01-17
5.15 |  | Implement "Manage News" function | 2017-01-17 | 2017-01-21 | 5 | bar: 2017-01-17 to 2017-01-21
5.16 |  | Team Meeting | 2017-01-23 | 2017-01-23 | 1 | bar: 2017-01-23
5.17 |  | Mentor Meeting | 2017-01-23 | 2017-01-23 | 1 | bar: 2017-01-23
5.18 |  | Training Technical | 2017-01-24 | 2017-01-24 | 1 | bar: 2017-01-24
5.19 |  | Implement "Manage Account" function | 2017-01-24 | 2017-01-28 | 5 | bar: 2017-01-24 to 2017-01-28
5.20 |  | Tet Holiday | 2017-01-30 | 2017-02-05 | 7
5.21 |  | Team Meeting | 2017-02-06 | 2017-02-06 | 1 | bar: 2017-02-06
5.22 |  | Mentor Meeting | 2017-02-06 | 2017-02-06 | 1 | bar: 2017-02-06
5.23 |  | Training Technical | 2017-02-07 | 2017-02-07 | 1 | bar: 2017-02-07
5.24 |  | Implement "Manage Homepage" function | 2017-02-07 | 2017-02-11 | 5 | bar: 2017-02-07 to 2017-02-11
5.25 |  | Team Meeting | 2017-02-13 | 2017-02-13 | 1 | bar: 2017-02-13
5.26 |  | Mentor Meeting | 2017-02-13 | 2017-02-13 | 1 | bar: 2017-02-13
5.27 |  | Training Technical | 2017-02-14 | 2017-02-14 | 1 | bar: 2017-02-14
5.28 |  | Implement "Manage Category" function | 2017-02-14 | 2017-02-18 | 5 | bar: 2017-02-14 to 2017-02-18
5.29 |  | Team Meeting | 2017-02-20 | 2017-02-20 | 1 | bar: 2017-02-20
5.30 |  | Mentor Meeting | 2017-02-20 | 2017-02-20 | 1 | bar: 2017-02-20
5.31 |  | Training Technical | 2017-02-21 | 2017-02-21 | 1 | bar: 2017-02-21
5.32 |  | Test | 2017-02-21 | 2017-02-25 | 5 | bar: 2017-02-21 to 2017-02-25
6 | INCREMENTAL 2 | INCREMENTAL 2 | 2017-02-27 | 2017-03-26 | 28 | bar: 2017-02-27 to 2017-03-26
6.1 |  | Team Meeting | 2017-02-27 | 2017-02-27 | 1 | bar: 2017-02-27
6.2 |  | Mentor Meeting | 2017-02-27 | 2017-02-27 | 1 | bar: 2017-02-27
6.3 |  | Training Technical | 2017-02-28 | 2017-02-28 | 1 | bar: 2017-02-28
6.4 |  | Draw Class diagram | 2017-02-28 | 2017-02-28 | 1 | bar: 2017-02-28
6.5 |  | Draw Sequence diagram | 2017-02-28 | 2017-03-01 | 2 | bar: 2017-02-28 to 2017-03-01
6.6 |  | Design Database | 2017-02-28 | 2017-03-01 | 2 | bar: 2017-02-28 to 2017-03-01
6.7 |  | Create User Interface | 2017-03-01 | 2017-03-04 | 4 | bar: 2017-03-01 to 2017-03-04
6.8 |  | Team Meeting | 2017-03-06 | 2017-03-06 | 1 | bar: 2017-03-06
6.9 |  | Mentor Meeting | 2017-03-06 | 2017-03-06 | 1 | bar: 2017-03-06
6.10 |  | Training Technical | 2017-03-07 | 2017-03-07 | 1 | bar: 2017-03-07
6.11 |  | Implement "Manage Banners" function | 2017-03-06 | 2017-03-11 | 6 | bar: 2017-03-06 to 2017-03-11
6.12 |  | Team Meeting | 2017-03-13 | 2017-03-13 | 1 | bar: 2017-03-13
6.13 |  | Mentor Meeting | 2017-03-13 | 2017-03-13 | 1 | bar: 2017-03-13
6.14 |  | Training Technical | 2017-03-14 | 2017-03-14 | 1 | bar: 2017-03-14
6.15 |  | Implement "Manage Popups" function | 2017-03-13 | 2017-03-18 | 6 | bar: 2017-03-14 to 2017-03-18
6.16 |  | Implement "Manage FAQ" function | 2017-03-13 | 2017-03-18 | 6 | bar: 2017-03-14 to 2017-03-18
6.17 |  | Team Meeting | 2017-03-20 | 2017-03-20 | 1 | bar: 2017-03-20
6.18 |  | Mentor Meeting | 2017-03-20 | 2017-03-20 | 1 | bar: 2017-03-20
6.19 |  | Training Technical | 2017-03-21 | 2017-03-21 | 1 | bar: 2017-03-21
6.20 |  | Test | 2017-03-20 | 2017-03-25 | 6 | bar: 2017-03-20 to 2017-03-25
6.21 |  | Customer Meeting | 2017-03-25 | 2017-03-25 | 1 | bar: 2017-03-25
7 | INCREMENTAL 3 | INCREMENTAL3 | 2017-03-27 | 2017-04-23 | 28 | bar: 2017-03-27 to 2017-04-23
7.1 |  | Team Meeting | 2017-03-27 | 2017-03-27 | 1 | bar: 2017-03-27
7.2 |  | Mentor Meeting | 2017-03-27 | 2017-03-27 | 1 | bar: 2017-03-27
7.3 |  | Training Technical | 2017-03-28 | 2017-03-28 | 1 | bar: 2017-03-28
7.4 |  | Draw Class diagram | 2017-03-28 | 2017-03-29 | 2 | bar: 2017-03-28 to 2017-03-29
7.5 |  | Draw Sequence diagram | 2017-03-29 | 2017-03-30 | 2 | bar: 2017-03-29 to 2017-03-30
7.6 |  | Design Database | 2017-03-31 | 2017-03-31 | 1 | bar: 2017-03-31
7.7 |  | Create User Interface | 2017-03-27 | 2017-04-01 | 6 | bar: 2017-03-27 to 2017-04-01
7.8 |  | Team Meeting | 2017-04-03 | 2017-04-03 | 1 | bar: 2017-04-03
7.9 |  | Mentor Meeting | 2017-04-03 | 2017-04-03 | 1 | bar: 2017-04-03
7.10 |  | Training Technical | 2017-04-04 | 2017-04-04 | 1 | bar: 2017-04-04
7.11 |  | Implement "Manage Examination" function | 2017-04-03 | 2017-04-08 | 6 | bar: 2017-04-03 to 2017-04-08
7.12 |  | Team Meeting | 2017-04-10 | 2017-04-10 | 1 | bar: 2017-04-10
7.13 |  | Mentor Meeting | 2017-04-10 | 2017-04-10 | 1 | bar: 2017-04-10
7.14 |  | Training Technical | 2017-04-11 | 2017-04-11 | 1 | bar: 2017-04-11
7.15 |  | Implement "Manage Examination" function | 2017-04-10 | 2017-04-15 | 6 | bar: 2017-04-10 to 2017-04-15
7.16 |  | Team Meeting | 2017-04-17 | 2017-04-17 | 1 | bar: 2017-04-17
7.17 |  | Mentor Meeting | 2017-04-17 | 2017-04-17 | 1 | bar: 2017-04-17
7.18 |  | Training Technical | 2017-04-18 | 2017-04-18 | 1 | bar: 2017-04-18
7.19 |  | Test | 2017-04-17 | 2017-04-21 | 5 | bar: 2017-04-17 to 2017-04-21
7.20 |  | Customer Meeting | 2017-04-22 | 2017-04-22 | 1 | bar: 2017-04-22
8 | CLOSURE | CLOSURE | 2017-04-24 | 2017-04-30 | 7 | bar: 2017-04-24 to 2017-04-30
8.1 |  | Team Meeting | 2017-04-24 | 2017-04-24 | 1 | bar: 2017-04-24
8.2 |  | Mentor Meeting | 2017-04-24 | 2017-04-24 | 1 | bar: 2017-04-24
8.3 |  | Monitoring and Controlling | 2017-04-25 | 2017-04-27 | 3 | bar: 2017-04-25
8.4 |  | Deploy User Guide | 2017-04-27 | 2017-04-27 | 1 | bar: 2017-04-25 to 2017-04-27
8.5 |  | Deploy Installation Guide | 2017-04-28 | 2017-04-28 | 1 | bar: 2017-04-28