## Report
WEEKLY REPORT
WEEK: 1
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 2016-03-10 | 2016-03-10 | HaiTran | 1 | 1
2 | Develop Team rule & policy | 2016-03-10 | 2016-04-10 |  | 2 | 2
3 | Review Team rule & policy | 2016-05-10 | 2016-05-10 |  | 3 | 4
4 | Mentor Meeting | 2016-06-10 | 2016-06-10 |  | 2 | 3
5 | Define Process Decision | 2016-07-10 | 2016-08-10 |  | 2 | 3
6 | Team Meeting | 2016-03-10 | 2016-03-10 | HienNguyen | 1 | 1
7 | Develop Team rule & policy | 2016-03-10 | 2016-04-10 |  | 4 | 2
8 | Review Team rule & policy | 2016-05-10 | 2016-05-10 |  | 3 | 4
9 | Mentor Meeting | 2016-06-10 | 2016-06-10 |  | 2 | 3
10 | Develop Team Charter | 2016-06-10 | 2016-07-10 |  | 4 | 3
11 | Develop Project Charter | 2016-06-10 | 2016-07-10 |  | 3 | 2
12 | Define Process Decision | 2016-07-10 | 2016-08-10 |  | 3 | 4
13 | Team Meeting | 2016-03-10 | 2016-03-10 | KhoiNguyen | 1 | 1
14 | Develop Team rule & policy | 2016-03-10 | 2016-04-10 |  | 1 | 2
15 | Review Team rule & policy | 2016-05-10 | 2016-05-10 |  | 3 | 4
16 | Mentor Meeting | 2016-06-10 | 2016-06-10 |  | 2 | 3
17 | Define Process Decision | 2016-07-10 | 2016-08-10 |  | 2 | 5
18 | Team Meeting | 2016-03-10 | 2016-03-10 | MinhDoan | 1 | 1
19 | Develop Team rule & policy | 2016-03-10 | 2016-04-10 |  | 3 | 2
20 | Review Team rule & policy | 2016-05-10 | 2016-05-10 |  | 3 | 4
21 | Mentor Meeting | 2016-06-10 | 2016-06-10 |  | 2 | 3
22 | Define Process Decision | 2016-07-10 | 2016-08-10 |  | 4 | 3
23 | Team Meeting | 2016-03-10 | 2016-03-10 | TaiNguyen | 1 | 1
24 | Develop Team rule & policy | 2016-03-10 | 2016-04-10 |  | 3 | 2
25 | Review Team rule & policy | 2016-05-10 | 2016-05-10 |  | 3 | 4
26 | Mentor Meeting | 2016-06-10 | 2016-06-10 |  | 2 | 3
27 | Define Process Decision | 2016-07-10 | 2016-08-10 |  | 3 | 5
28 | Team Meeting | 2016-03-10 | 2016-03-10 | XuanThaiHien | 1 | 1
29 | Develop Team rule & policy | 2016-03-10 | 2016-04-10 |  | 2 | 2
30 | Review Team rule & policy | 2016-05-10 | 2016-05-10 |  | 3 | 4
31 | Mentor Meeting | 2016-06-10 | 2016-06-10 |  | 2 | 3
32 | Define Process Decision | 2016-07-10 | 2016-08-10 |  | 3 | 2
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 10 | 13
|  |  |  | HienNguyen | 20 | 19
|  |  |  | KhoiNguyen | 9 | 15
|  |  |  | MinhDoan | 13 | 13
|  |  |  | TaiNguyen | 12 | 15
|  |  |  | XuanThaiHien | 11 | 12

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time