## Sheet1
EFFORT LOG
WEEK: 11
No. | Task | From | To | Estimate Time | Actual Time
1 | Team Meeting | 2016-12-12 | 2016-12-12 | 2 | 2
2 | Review Usecase description "Manage News" Function | 2016-12-12 | 2016-12-12 | 4 | 5
3 | Review Usecase description "Manage Q&A" Function | 13/12/2016 | 13/12/2016 | 4 | 3
4 | Review Usecase description "Manage Categories" Function | 13/12/2016 | 13/12/2016 | 4 | 5
5 | Training Technical | 13/12/2016 | 13/12/2016 | 2 | 2
6 | Review Usecase Diagram "Manage News" Function | 14/12/2016 | 14/12/2016 | 6 | 5
7 | Define Operating environment | 15/12/2016 | 15/12/2016 | 2 | 1
8 | Develop UI "Manage News" Function | 16/12/2016 | 17/12/2016 | 6 | 8