## Sheet1
EFFORT LOG
WEEK: 12
No. | Task | From | To | Estimate Time | Actual Time
1 | Team Meeting | 19/12/2016 | 19/12/2016 | 2 | 2
2 | Update Usecase description "Manage Homepage" Function | 19/12/2016 | 19/12/2016 | 2 | 3
3 | Update Usecase Diagram "Manage Q&A" Function | 20/12/2016 | 20/12/2016 | 3 | 2
4 | Training Technical | 20/12/2016 | 20/12/2016 | 2 | 2
5 | Customer Meeting | 21/12/2016 | 21/12/2016 | 3 | 2
6 | Develop "Manage Homepage" Functional Testcase | 21/12/2016 | 23/12/2016 | 5 | 6
7 | Develop "Manage Homepage" User Acceptance Testcase | 21/12/2016 | 24/12/2016 | 6 | 5