## Sheet1
EFFORT LOG
WEEK: 12
No. | Task | From | To | Estimate Time | Actual Time
1 | Update Usecase description "Manage Examination" Function | 19/12/2016 | 19/12/2016 | 2 | 3
2 | Update Usecase Diagram "Manage Examination" Function | 20/12/2016 | 20/12/2016 | 3 | 2
3 | Develop "Manage Examination" Functional Testcase | 21/12/2016 | 23/12/2016 | 4 | 4
4 | Develop "Manage Q&A" Functional Testcase | 21/12/2016 | 24/12/2016 | 5 | 6
5 | Develop "Manage Examination" User Acceptance Testcase | 21/12/2016 | 24/12/2016 | 6 | 4