## Report
WEEKLY REPORT
WEEK: 12
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 19/12/2016 | 19/12/2016 | HaiTran | 2 | 2
2 | Update Usecase description "Manage News" Function | 19/12/2016 | 19/12/2016 |  | 4 | 4
3 | Update Usecase description "Manage Categories" Function | 19/12/2016 | 19/12/2016 |  | 3 | 4
4 | Update Usecase Diagram "Manage News" Function | 20/12/2016 | 20/12/2016 |  | 2 | 2
5 | Update Usecase Diagram "Manage Languages" Function | 20/12/2016 | 20/12/2016 |  | 1 | 2
6 | Training Technical | 20/12/2016 | 20/12/2016 |  | 2 | 2
7 | Customer Meeting | 21/12/2016 | 21/12/2016 |  | 3 | 2
8 | Develop "Manage News" Functional Testcase | 21/12/2016 | 23/12/2016 |  | 7 | 8
9 | Develop "Manage Account" User Acceptance Testcase | 21/12/2016 | 24/12/2016 |  | 7 | 6
10 | Develop "Manage Languages" User Acceptance Testcase | 21/12/2016 | 24/12/2016 |  | 2 | 2
11 | Team Meeting | 19/12/2016 | 19/12/2016 | HienNguyen | 2 | 2
12 | Update Usecase description "Manage Accounts" Function | 19/12/2016 | 19/12/2016 |  | 3 | 4
13 | Update Usecase Diagram "Manage Accouts" Function | 20/12/2016 | 20/12/2016 |  | 2 | 3
14 | Training Technical | 20/12/2016 | 20/12/2016 |  | 2 | 2
15 | Customer Meeting | 21/12/2016 | 21/12/2016 |  | 3 | 2
16 | Develop "Manage Account" Functional Testcase | 21/12/2016 | 23/12/2016 |  | 6 | 6
17 | Develop "Manage News" User Acceptance Testcase | 21/12/2016 | 24/12/2016 |  | 7 | 5
18 | Team Meeting | 19/12/2016 | 19/12/2016 | KhoiNguyen | 2 | 2
19 | Update Usecase description "Manage Q&A" Function | 19/12/2016 | 19/12/2016 |  | 2 | 3
20 | Update Usecase description "Manage Languages" Function | 19/12/2016 | 19/12/2016 |  | 2 | 1
21 | Update Usecase Diagram "Manage Homepage" Function | 20/12/2016 | 20/12/2016 |  | 2 | 2
22 | Update Usecase Diagram "Manage Categories" Function | 20/12/2016 | 20/12/2016 |  | 3 | 3
23 | Training Technical | 20/12/2016 | 20/12/2016 |  | 2 | 2
24 | Customer Meeting | 21/12/2016 | 21/12/2016 |  | 3 | 2
25 | Develop "Manage Categories" Functional Testcase | 21/12/2016 | 23/12/2016 |  | 6 | 7
26 | Develop "Manage Languages" Functional Testcase | 21/12/2016 | 24/12/2016 |  | 3 | 2
27 | Develop "Manage Categories" User Acceptance Testcase | 21/12/2016 | 24/12/2016 |  | 6 | 6
28 | Develop "Manage Q&A" User Acceptance Testcase | 21/12/2016 | 24/12/2016 |  | 3 | 5
29 | Team Meeting | 19/12/2016 | 19/12/2016 | MinhDoan | 2 | 2
30 | Update Usecase description "Manage Banners" Function | 19/12/2016 | 19/12/2016 |  | 2 | 3
31 | Update Usecase description "Manage Pop-ups Function | 19/12/2016 | 19/12/2016 |  | 2 | 3
32 | Update Usecase Diagram "Manage Banners" Function | 20/12/2016 | 20/12/2016 |  | 2 | 3
33 | Update Usecase Diagram "Manage Pop-ups" Function | 20/12/2016 | 20/12/2016 |  | 3 | 2
34 | Training Technical | 20/12/2016 | 20/12/2016 |  | 2 | 2
35 | Customer Meeting | 21/12/2016 | 21/12/2016 |  | 3 | 2
36 | Develop "Manage Banners" Functional Testcase | 21/12/2016 | 23/12/2016 |  | 6 | 5
37 | Develop "Manage Pop-ups" Functional Testcase | 21/12/2016 | 23/12/2016 |  | 6 | 7
38 | Develop "Manage Banners" User Acceptance Testcase | 21/12/2016 | 24/12/2016 |  | 3 | 4
39 | Develop "Manage Pop-ups" User Acceptance Testcase | 21/12/2016 | 24/12/2016 |  | 3 | 4
40 | Team Meeting | 19/12/2016 | 19/12/2016 | TaiNguyen | 2 | 2
41 | Update Usecase description "Manage Homepage" Function | 19/12/2016 | 19/12/2016 |  | 2 | 3
42 | Update Usecase Diagram "Manage Q&A" Function | 20/12/2016 | 20/12/2016 |  | 3 | 2
43 | Training Technical | 20/12/2016 | 20/12/2016 |  | 2 | 2
44 | Customer Meeting | 21/12/2016 | 21/12/2016 |  | 3 | 2
45 | Develop "Manage Homepage" Functional Testcase | 21/12/2016 | 23/12/2016 |  | 5 | 6
46 | Develop "Manage Homepage" User Acceptance Testcase | 21/12/2016 | 24/12/2016 |  | 6 | 5
47 | Update Usecase description "Manage Examination" Function | 19/12/2016 | 19/12/2016 | XuanThaiHien | 2 | 3
48 | Update Usecase Diagram "Manage Examination" Function | 20/12/2016 | 20/12/2016 |  | 3 | 2
49 | Develop "Manage Examination" Functional Testcase | 21/12/2016 | 23/12/2016 |  | 4 | 4
50 | Develop "Manage Q&A" Functional Testcase | 21/12/2016 | 24/12/2016 |  | 5 | 6
51 | Develop "Manage Examination" User Acceptance Testcase | 21/12/2016 | 24/12/2016 |  | 6 | 4
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 33 | 34
|  |  |  | HienNguyen | 25 | 24
|  |  |  | KhoiNguyen | 34 | 35
|  |  |  | MinhDoan | 34 | 37
|  |  |  | TaiNguyen | 23 | 22
|  |  |  | XuanThaiHien | 20 | 19

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time