## Sheet1
EFFORT LOG
WEEK: 13
No. | Task | From | To | Estimate Time | Actual Time
1 | Team Meeting | 26/12/2016 | 26/12/2016 | 2 | 2
2 | Review "Manage Homepage" Functional Testcase | 26/12/2016 | 26/12/2016 | 4 | 3
3 | Review "Manage Categories" Functional Testcase | 27/12/2016 | 27/12/2016 | 3 | 3
4 | Training Technical | 27/12/2016 | 27/12/2016 | 2 | 2
5 | Review "Manage Q&A" Functional Testcase | 28/12/2016 | 28/12/2016 | 3 | 2
6 | Review "Manage News" User Acceptance Testcase | 28/12/2016 | 28/12/2016 | 5 | 6
7 | Review "Manage Examination" User Acceptance Testcase | 29/12/2016 | 29/12/2016 | 3 | 4
8 | Update "Manage Categories" Functional Testcase | 29/12/2016 | 29/12/2016 | 3 | 2
9 | Update "Manage Languages" Functional Testcase | 29/12/2016 | 29/12/2016 | 2 | 1
10 | Collect Testcase | 29/12/2016 | 29/12/2016 | 1 | 2
11 | Research Physical view | 30/12/2016 | 31/12/2016 | 4 | 3
12 | Draw Physical view draft | 30/12/2016 | 31/12/2016 | 3 | 4