## Sheet1
EFFORT LOG
WEEK: 13
No. | Task | From | To | Estimate Time | Actual Time
1 | Team Meeting | 26/12/2016 | 26/12/2016 | 2 | 2
2 | Review "Manage Account" Functional Testcase | 26/12/2016 | 26/12/2016 | 4 | 5
3 | Review "Manage Banners" Functional Testcase | 27/12/2016 | 27/12/2016 | 2 | 2
4 | Review "Manage Examination" Functional Testcase | 27/12/2016 | 27/12/2016 | 1 | 2
5 | Training Technical | 27/12/2016 | 27/12/2016 | 2 | 2
6 | Review "Manage Q&A" Functional Testcase | 28/12/2016 | 28/12/2016 | 2 | 3
7 | Review "Manage Homepage" User Acceptance Testcase | 28/12/2016 | 28/12/2016 | 3 | 4
8 | Review "Manage Pop-ups" User Acceptance Testcase | 29/12/2016 | 29/12/2016 | 2 | 3
9 | Review "Manage Languages" User Acceptance Testcase | 29/12/2016 | 29/12/2016 | 1 | 1
10 | Update "Manage Banners" Functional Testcase | 29/12/2016 | 29/12/2016 | 2 | 2
11 | Update "Manage Pop-ups" Functional Testcase | 29/12/2016 | 29/12/2016 | 2 | 3
12 | Research Dynamic view | 30/12/2016 | 31/12/2016 | 6 | 4
13 | Draw Dynamic view draft | 30/12/2016 | 31/12/2016 | 5 | 4