## Report
WEEKLY REPORT
WEEK: 13
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 26/12/2016 | 26/12/2016 | HaiTran | 2 | 2
2 | Review "Manage News" Functional Testcase | 26/12/2016 | 26/12/2016 |  | 4 | 5
3 | Review "Manage Pop-ups" Functional Testcase | 27/12/2016 | 27/12/2016 |  | 2 | 2
4 | Training Technical | 27/12/2016 | 27/12/2016 |  | 2 | 2
5 | Review "Manage Account" User Acceptance Testcase | 28/12/2016 | 28/12/2016 |  | 5 | 6
6 | Review "Manage Banners" User Acceptance Testcase | 28/12/2016 | 28/12/2016 |  | 2 | 3
7 | Review "Manage Examination" User Acceptance Testcase | 29/12/2016 | 29/12/2016 |  | 2 | 3
8 | Review "Manage Q&A" User Acceptance Testcase | 29/12/2016 | 29/12/2016 |  | 2 | 3
9 | Update "Manage News" Functional Testcase | 29/12/2016 | 29/12/2016 |  | 3 | 3
10 | Research Static view | 30/12/2016 | 31/12/2016 |  | 5 | 4
11 | Writting rationel | 30/12/2016 | 31/12/2016 |  | 3 | 1
12 | Team Meeting | 26/12/2016 | 26/12/2016 | HienNguyen | 2 | 2
13 | Review "Manage News" Functional Testcase | 26/12/2016 | 26/12/2016 |  | 3 | 6
14 | Review "Manage Categories" Functional Testcase | 27/12/2016 | 27/12/2016 |  | 3 | 4
15 | Training Technical | 27/12/2016 | 27/12/2016 |  | 2 | 2
16 | Review "Manage Languages" Functional Testcase | 28/12/2016 | 28/12/2016 |  | 1 | 2
17 | Review "Manage News" User Acceptance Testcase | 28/12/2016 | 28/12/2016 |  | 4 | 6
18 | Review "Manage Categories" User Acceptance Testcase | 29/12/2016 | 29/12/2016 |  | 5 | 6
19 | Review "Manage Languages" User Acceptance Testcase | 29/12/2016 | 29/12/2016 |  | 1 | 1
20 | Update "Manage Account" Functional Testcase | 29/12/2016 | 29/12/2016 |  | 2 | 3
21 | Research Physical view | 30/12/2016 | 31/12/2016 |  | 3 | 5
22 | Draw Physical view draft | 30/12/2016 | 31/12/2016 |  | 3 | 4
23 | Team Meeting | 26/12/2016 | 26/12/2016 | KhoiNguyen | 2 | 2
24 | Review "Manage Homepage" Functional Testcase | 26/12/2016 | 26/12/2016 |  | 4 | 3
25 | Review "Manage Categories" Functional Testcase | 27/12/2016 | 27/12/2016 |  | 3 | 3
26 | Training Technical | 27/12/2016 | 27/12/2016 |  | 2 | 2
27 | Review "Manage Q&A" Functional Testcase | 28/12/2016 | 28/12/2016 |  | 3 | 2
28 | Review "Manage News" User Acceptance Testcase | 28/12/2016 | 28/12/2016 |  | 5 | 6
29 | Review "Manage Examination" User Acceptance Testcase | 29/12/2016 | 29/12/2016 |  | 3 | 4
30 | Update "Manage Categories" Functional Testcase | 29/12/2016 | 29/12/2016 |  | 3 | 2
31 | Update "Manage Languages" Functional Testcase | 29/12/2016 | 29/12/2016 |  | 2 | 1
32 | Collect Testcase | 29/12/2016 | 29/12/2016 |  | 1 | 2
33 | Research Physical view | 30/12/2016 | 31/12/2016 |  | 4 | 3
34 | Draw Physical view draft | 30/12/2016 | 31/12/2016 |  | 3 | 4
35 | Team Meeting | 26/12/2016 | 26/12/2016 | MinhDoan | 2 | 2
36 | Review "Manage Account" Functional Testcase | 26/12/2016 | 26/12/2016 |  | 4 | 5
37 | Review "Manage Banners" Functional Testcase | 27/12/2016 | 27/12/2016 |  | 2 | 2
38 | Review "Manage Examination" Functional Testcase | 27/12/2016 | 27/12/2016 |  | 1 | 2
39 | Training Technical | 27/12/2016 | 27/12/2016 |  | 2 | 2
40 | Review "Manage Q&A" Functional Testcase | 28/12/2016 | 28/12/2016 |  | 2 | 3
41 | Review "Manage Homepage" User Acceptance Testcase | 28/12/2016 | 28/12/2016 |  | 3 | 4
42 | Review "Manage Pop-ups" User Acceptance Testcase | 29/12/2016 | 29/12/2016 |  | 2 | 3
43 | Review "Manage Languages" User Acceptance Testcase | 29/12/2016 | 29/12/2016 |  | 1 | 1
44 | Update "Manage Banners" Functional Testcase | 29/12/2016 | 29/12/2016 |  | 2 | 2
45 | Update "Manage Pop-ups" Functional Testcase | 29/12/2016 | 29/12/2016 |  | 2 | 3
46 | Research Dynamic view | 30/12/2016 | 31/12/2016 |  | 6 | 4
47 | Draw Dynamic view draft | 30/12/2016 | 31/12/2016 |  | 5 | 4
48 | Team Meeting | 26/12/2016 | 26/12/2016 | TaiNguyen | 2 | 2
49 | Review "Manage Account" Functional Testcase | 26/12/2016 | 26/12/2016 |  | 5 | 7
50 | Review "Manage Pop-ups" Functional Testcase | 27/12/2016 | 27/12/2016 |  | 2 | 1
51 | Review "Manage Examination" Functional Testcase | 27/12/2016 | 27/12/2016 |  | 2 | 2
52 | Training Technical | 27/12/2016 | 27/12/2016 |  | 2 | 2
53 | Review "Manage Account" User Acceptance Testcase | 28/12/2016 | 28/12/2016 |  | 4 | 6
54 | Review "Manage Homepage" User Acceptance Testcase | 28/12/2016 | 28/12/2016 |  | 2 | 3
55 | Review "Manage Categories" User Acceptance Testcase | 29/12/2016 | 29/12/2016 |  | 4 | 6
56 | Review "Manage Q&A" User Acceptance Testcase | 29/12/2016 | 29/12/2016 |  | 2 | 2
57 | Update "Manage Homepage" Functional Testcase | 29/12/2016 | 29/12/2016 |  | 2 | 2
58 | Research Static view | 30/12/2016 | 31/12/2016 |  | 4 | 5
59 | Draw Static view draft | 30/12/2016 | 31/12/2016 |  | 4 | 3
60 | Review "Manage Homepage" Functional Testcase | 26/12/2016 | 26/12/2016 | XuanThaiHien | 2 | 2
61 | Review "Manage Banners" Functional Testcase | 27/12/2016 | 27/12/2016 |  | 3 | 2
62 | Review "Manage Languages" Functional Testcase | 28/12/2016 | 28/12/2016 |  | 1 | 1
63 | Review "Manage Banners" User Acceptance Testcase | 28/12/2016 | 28/12/2016 |  | 2 | 1
64 | Review "Manage Pop-ups" User Acceptance Testcase | 29/12/2016 | 29/12/2016 |  | 2 | 1
65 | Update "Manage Examination" Functional Testcase | 29/12/2016 | 29/12/2016 |  | 3 | 3
66 | Update "Manage Q&A" Functional Testcase | 29/12/2016 | 29/12/2016 |  | 3 | 2
67 | Research Dynamic view | 30/12/2016 | 31/12/2016 |  | 3 | 4
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 32 | 34
|  |  |  | HienNguyen | 29 | 41
|  |  |  | KhoiNguyen | 35 | 34
|  |  |  | MinhDoan | 34 | 37
|  |  |  | TaiNguyen | 35 | 41
|  |  |  | XuanThaiHien | 19 | 16

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time