## Report
WEEKLY REPORT
WEEK: 15
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 2017-09-01 | 2017-09-01 | HaiTran | 2 | 2
2 | Update Static View | 2017-09-01 | 2017-09-01 |  | 6 | 5
3 | Customer Meeting | 2017-10-01 | 2017-10-01 |  | 2 | 2
4 | Training Technical | 2017-10-01 | 2017-10-01 |  | 2 | 2
5 | Research MongoDB | 2017-11-01 | 2017-11-01 |  | 3 | 2
6 | Update Dynamic View | 2017-11-01 | 2017-11-01 |  | 4 | 5
7 | Mentor Meeting | 2017-12-01 | 2017-12-01 |  | 2 | 4
8 | Team Meeting | 2017-09-01 | 2017-09-01 | HienNguyen | 2 | 2
9 | Update Physical View | 2017-09-01 | 2017-09-01 |  | 3 | 4
10 | Customer Meeting | 2017-10-01 | 2017-10-01 |  | 2 | 2
11 | Training Technical | 2017-10-01 | 2017-10-01 |  | 2 | 2
12 | Research Redis Technology | 2017-11-01 | 2017-11-01 |  | 3 | 4
13 | Mentor Meeting | 2017-12-01 | 2017-12-01 |  | 2 | 4
14 | Team Meeting | 2017-09-01 | 2017-09-01 | KhoiNguyen | 2 | 2
15 | Update Dynamic View | 2017-09-01 | 2017-09-01 |  | 4 | 6
16 | Customer Meeting | 2017-10-01 | 2017-10-01 |  | 2 | 2
17 | Training Technical | 2017-10-01 | 2017-10-01 |  | 2 | 2
18 | Update Physical View | 2017-11-01 | 2017-11-01 |  | 3 | 4
19 | Mentor Meeting | 2017-12-01 | 2017-12-01 |  | 2 | 4
20 | Team Meeting | 2017-09-01 | 2017-09-01 | MinhDoan | 2 | 2
21 | Customer Meeting | 2017-10-01 | 2017-10-01 |  | 2 | 2
22 | Training Technical | 2017-10-01 | 2017-10-01 |  | 2 | 2
23 | Mentor Meeting | 2017-12-01 | 2017-12-01 |  | 2 | 4
24 | Team Meeting | 2017-09-01 | 2017-09-01 | TaiNguyen | 2 | 2
25 | Customer Meeting | 2017-10-01 | 2017-10-01 |  | 2 | 2
26 | Training Technical | 2017-10-01 | 2017-10-01 |  | 2 | 2
27 | Research Elastic Technology | 2017-11-01 | 2017-11-01 |  | 3 | 3
28 | Update Static View | 2017-11-01 | 2017-11-01 |  | 3 | 3
29 | Mentor Meeting | 2017-12-01 | 2017-12-01 |  | 2 | 4
30 | Mentor Meeting | 2017-12-01 | 2017-12-01 | XuanThaiHien | 2 | 4
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 21 | 22
|  |  |  | HienNguyen | 14 | 18
|  |  |  | KhoiNguyen | 15 | 20
|  |  |  | MinhDoan | 8 | 10
|  |  |  | TaiNguyen | 14 | 16
|  |  |  | XuanThaiHien | 2 | 4

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time