## Sheet1
EFFORT LOG
WEEK: 16
No. | Task | From | To | Estimate Time | Actual Time
1 | Team Meeting | 16/1/2017 | 16/1/2017 | 2 | 2
2 | Draw class diagram function "Manage News" | 16/1/2017 | 16/1/2017 | 4 | 5
3 | Draw class diagram function "Manage Banners" | 16/1/2017 | 16/1/2017 | 3 | 3
4 | Training Technical | 17/1/2017 | 17/1/2017 | 2 | 2
5 | Draw sequence diagram function "Manage Banners" | 18/1/2017 | 18/1/2017 | 2 | 4
6 | Draw sequence diagram function "Manage Examination" | 18/1/2017 | 18/1/2017 | 3 | 4
7 | Mentor Meeting | 19/1/2017 | 19/1/2017 | 2 | 3
8 | Review class diagram function "Manage Account" | 19/1/2017 | 19/1/2017 | 3 | 2
9 | Review class diagram function "Manage Categories" | 19/1/2017 | 19/1/2017 | 3 | 3
10 | Review sequence diagram function "Manage Account" | 20/1/2017 | 20/1/2017 | 3 | 4
11 | Review sequence diagram function "Manage Popups" | 20/1/2017 | 20/1/2017 | 2 | 2
12 | Update sequence diagram function "Manage Account" | 21/1/2017 | 21/1/2017 | 4 | 6