## Sheet1
EFFORT LOG
WEEK: 16
No. | Task | From | To | Estimate Time | Actual Time
1 | Team Meeting | 16/1/2017 | 16/1/2017 | 2 | 2
2 | Design Database | 16/1/2017 | 16/1/2017 | 3 | 3
3 | Draw class diagram function "Manage Account" | 16/1/2017 | 16/1/2017 | 5 | 6
4 | Draw class diagram function "Manage Categories" | 16/1/2017 | 16/1/2017 | 5 | 7
5 | Training Technical | 17/1/2017 | 17/1/2017 | 2 | 2
6 | Draw class diagram function "Manage Languages" | 17/1/2017 | 17/1/2017 | 2 | 1
7 | Mentor Meeting | 19/1/2017 | 19/1/2017 | 2 | 3
8 | Review class diagram function "Manage Account" | 19/1/2017 | 19/1/2017 | 2 | 2
9 | Review class diagram function "Manage Categories" | 19/1/2017 | 19/1/2017 | 2 | 3
10 | Review sequence diagram function "Manage Account" | 20/1/2017 | 20/1/2017 | 4 | 5
11 | Review sequence diagram function "Manage News" | 20/1/2017 | 20/1/2017 | 4 | 4
12 | Review sequence diagram function "Manage Banners" | 20/1/2017 | 20/1/2017 | 2 | 2
13 | Review class diagram function "Manage Account" | 21/1/2017 | 21/1/2017 | 5 | 5