## Sheet1
EFFORT LOG
WEEK: 16
No. | Task | From | To | Estimate Time | Actual Time
1 | Draw class diagram function "Manage Examination" | 17/1/2017 | 17/1/2017 | 4 | 6
2 | Draw sequence diagram function "Manage Language" | 18/1/2017 | 18/1/2017 | 2 | 1
3 | Draw sequence diagram function "Manage FAQ" | 18/1/2017 | 18/1/2017 | 2 | 3
4 | Mentor Meeting | 19/1/2017 | 19/1/2017 | 2 | 3
5 | Review class diagram function "Manage FAQ" | 19/1/2017 | 19/1/2017 | 1 | 1
6 | Review class diagram function "Manage Languages" | 20/1/2017 | 20/1/2017 | 1 | 1
7 | Review sequence diagram function "Manage Examination" | 20/1/2017 | 20/1/2017 | 3 | 3
8 | Review sequence diagram function "Manage FAQ" | 20/1/2017 | 20/1/2017 | 2 | 2