## Report
WEEKLY REPORT
WEEK: 16
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 16/1/2017 | 16/1/2017 | HaiTran | 2 | 2
2 | Design Database | 16/1/2017 | 16/1/2017 |  | 2 | 3
3 | Training Technical | 17/1/2017 | 17/1/2017 |  | 2 | 2
4 | Draw sequence diagram function "Manage Account" | 17/1/2017 | 17/1/2017 |  | 5 | 7
5 | Draw sequence diagram function "Manage Homepage" | 18/1/2017 | 18/1/2017 |  | 4 | 5
6 | Mentor Meeting | 19/1/2017 | 19/1/2017 |  | 2 | 3
7 | Review class diagram function "Manage News" | 19/1/2017 | 19/1/2017 |  | 3 | 2
8 | Review class diagram function "Manage Banners" | 19/1/2017 | 19/1/2017 |  | 2 | 2
9 | Review class diagram function "Manage Popups" | 20/1/2017 | 20/1/2017 |  | 2 | 2
10 | Review sequence diagram function "Manage News" | 20/1/2017 | 20/1/2017 |  | 3 | 4
11 | Update sequence diagram function "Manage News" | 21/1/2017 | 21/1/2017 |  | 5 | 7
12 | Team Meeting | 16/1/2017 | 16/1/2017 | HienNguyen | 2 | 2
13 | Draw class diagram function "Manage News" | 16/1/2017 | 16/1/2017 |  | 4 | 5
14 | Draw class diagram function "Manage Banners" | 16/1/2017 | 16/1/2017 |  | 3 | 3
15 | Training Technical | 17/1/2017 | 17/1/2017 |  | 2 | 2
16 | Draw sequence diagram function "Manage Banners" | 18/1/2017 | 18/1/2017 |  | 2 | 4
17 | Draw sequence diagram function "Manage Examination" | 18/1/2017 | 18/1/2017 |  | 3 | 4
18 | Mentor Meeting | 19/1/2017 | 19/1/2017 |  | 2 | 3
19 | Review class diagram function "Manage Account" | 19/1/2017 | 19/1/2017 |  | 3 | 2
20 | Review class diagram function "Manage Categories" | 19/1/2017 | 19/1/2017 |  | 3 | 3
21 | Review sequence diagram function "Manage Account" | 20/1/2017 | 20/1/2017 |  | 3 | 4
22 | Review sequence diagram function "Manage Popups" | 20/1/2017 | 20/1/2017 |  | 2 | 2
23 | Update sequence diagram function "Manage Account" | 21/1/2017 | 21/1/2017 |  | 4 | 6
24 | Team Meeting | 16/1/2017 | 16/1/2017 | KhoiNguyen | 2 | 2
25 | Draw class diagram function "Manage Homepage" | 16/1/2017 | 16/1/2017 |  | 6 | 5
26 | Training Technical | 17/1/2017 | 17/1/2017 |  | 2 | 2
27 | Draw sequence diagram function "Manage News" | 17/1/2017 | 17/1/2017 |  | 5 | 6
28 | Mentor Meeting | 19/1/2017 | 19/1/2017 |  | 2 | 3
29 | Review class diagram function "Manage News" | 19/1/2017 | 19/1/2017 |  | 2 | 2
30 | Review sequence diagram function "Manage Categories" | 20/1/2017 | 20/1/2017 |  | 2 | 2
31 | Review sequence diagram function "Manage Language" | 20/1/2017 | 20/1/2017 |  | 2 | 1
32 | Update sequence diagram function "Manage Categories" | 21/1/2017 | 21/1/2017 |  | 4 | 4
33 | Team Meeting | 16/1/2017 | 16/1/2017 | MinhDoan | 2 | 2
34 | Draw class diagram function "Manage FAQ" | 16/1/2017 | 16/1/2017 |  | 7 | 6
35 | Training Technical | 17/1/2017 | 17/1/2017 |  | 2 | 2
36 | Draw class diagram function "Manage Popups" | 17/1/2017 | 17/1/2017 |  | 7 | 6
37 | Draw sequence diagram function "Manage Categories" | 18/1/2017 | 18/1/2017 |  | 7 | 8
38 | Draw sequence diagram function "Manage Popups" | 18/1/2017 | 18/1/2017 |  | 7 | 8
39 | Mentor Meeting | 19/1/2017 | 19/1/2017 |  | 2 | 3
40 | Review class diagram function "Manage FAQ" | 19/1/2017 | 19/1/2017 |  | 2 | 1
41 | Review class diagram function "Manage Homepage" | 19/1/2017 | 19/1/2017 |  | 2 | 2
42 | Review class diagram function "Manage Examination" | 20/1/2017 | 20/1/2017 |  | 2 | 3
43 | Review sequence diagram function "Manage Categories" | 20/1/2017 | 20/1/2017 |  | 2 | 3
44 | Review sequence diagram function "Manage Homepage" | 20/1/2017 | 20/1/2017 |  | 3 | 2
45 | Collect diagram into document | 21/1/2017 | 21/1/2017 |  | 2 | 2
46 | Team Meeting | 16/1/2017 | 16/1/2017 | TaiNguyen | 2 | 2
47 | Design Database | 16/1/2017 | 16/1/2017 |  | 3 | 3
48 | Draw class diagram function "Manage Account" | 16/1/2017 | 16/1/2017 |  | 5 | 6
49 | Draw class diagram function "Manage Categories" | 16/1/2017 | 16/1/2017 |  | 5 | 7
50 | Training Technical | 17/1/2017 | 17/1/2017 |  | 2 | 2
51 | Draw class diagram function "Manage Languages" | 17/1/2017 | 17/1/2017 |  | 2 | 1
52 | Mentor Meeting | 19/1/2017 | 19/1/2017 |  | 2 | 3
53 | Review class diagram function "Manage Account" | 19/1/2017 | 19/1/2017 |  | 2 | 2
54 | Review class diagram function "Manage Categories" | 19/1/2017 | 19/1/2017 |  | 2 | 3
55 | Review sequence diagram function "Manage Account" | 20/1/2017 | 20/1/2017 |  | 4 | 5
56 | Review sequence diagram function "Manage News" | 20/1/2017 | 20/1/2017 |  | 4 | 4
57 | Review sequence diagram function "Manage Banners" | 20/1/2017 | 20/1/2017 |  | 2 | 2
58 | Review class diagram function "Manage Account" | 21/1/2017 | 21/1/2017 |  | 5 | 5
59 | Draw class diagram function "Manage Examination" | 17/1/2017 | 17/1/2017 | XuanThaiHien | 4 | 6
60 | Draw sequence diagram function "Manage Language" | 18/1/2017 | 18/1/2017 |  | 2 | 1
61 | Draw sequence diagram function "Manage FAQ" | 18/1/2017 | 18/1/2017 |  | 2 | 3
62 | Mentor Meeting | 19/1/2017 | 19/1/2017 |  | 2 | 3
63 | Review class diagram function "Manage FAQ" | 19/1/2017 | 19/1/2017 |  | 1 | 1
64 | Review class diagram function "Manage Languages" | 20/1/2017 | 20/1/2017 |  | 1 | 1
65 | Review sequence diagram function "Manage Examination" | 20/1/2017 | 20/1/2017 |  | 3 | 3
66 | Review sequence diagram function "Manage FAQ" | 20/1/2017 | 20/1/2017 |  | 2 | 2
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 32 | 39
|  |  |  | HienNguyen | 33 | 40
|  |  |  | KhoiNguyen | 27 | 27
|  |  |  | MinhDoan | 47 | 48
|  |  |  | TaiNguyen | 40 | 45
|  |  |  | XuanThaiHien | 17 | 20

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time