## Report
WEEKLY REPORT
WEEK: 19
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 2017-06-02 | 2017-06-02 | HaiTran | 2 | 2
2 | Mentor Meeting | 2017-06-02 | 2017-06-02 |  | 2 | 4
3 | Training Technical | 2017-07-02 | 2017-07-02 |  | 2 | 2
4 | Implement"Deactivate Account" function | 2017-07-02 | 2017-08-02 |  | 16 | 15
5 | Demo "Login" function | 2017-09-02 | 2017-09-02 |  | 2 | 1
6 | Demo "Create Account" function | 2017-09-02 | 2017-09-02 |  | 1 | 1
7 | Demo " Show Account" function | 2017-09-02 | 2017-09-02 |  | 1 | 1
8 | Demo "Edit Account" function | 2017-09-02 | 2017-09-02 |  | 2 | 2
9 | Implement "Create draft" function | 2017-10-01 | 2017-11-01 |  | 15 | 16
10 | Team Meeting | 2017-06-02 | 2017-06-02 | HienNguyen | 2 | 2
11 | Mentor Meeting | 2017-06-02 | 2017-06-02 |  | 2 | 4
12 | Training Technical | 2017-07-02 | 2017-07-02 |  | 2 | 2
13 | Implement "Edit Account" function | 2017-07-02 | 2017-08-02 |  | 16 | 16
14 | Demo "Login" function | 2017-09-02 | 2017-09-02 |  | 2 | 1
15 | Demo "Create Account" function | 2017-09-02 | 2017-09-02 |  | 1 | 1
16 | Demo " Show Account" function | 2017-09-02 | 2017-09-02 |  | 1 | 1
17 | Demo "Edit Account" function | 2017-09-02 | 2017-09-02 |  | 2 | 2
18 | Implement "View News" function | 2017-10-01 | 2017-11-01 |  | 14 | 14
19 | Team Meeting | 2017-06-02 | 2017-06-02 | KhoiNguyen | 2 | 2
20 | Mentor Meeting | 2017-06-02 | 2017-06-02 |  | 2 | 4
21 | Training Technical | 2017-07-02 | 2017-07-02 |  | 2 | 2
22 | Implement "View List Account" function | 2017-07-02 | 2017-08-02 |  | 10 | 12
23 | Demo "Login" function | 2017-09-02 | 2017-09-02 |  | 2 | 1
24 | Demo "Create Account" function | 2017-09-02 | 2017-09-02 |  | 1 | 1
25 | Demo " Show Account" function | 2017-09-02 | 2017-09-02 |  | 1 | 1
26 | Demo "Edit Account" function | 2017-09-02 | 2017-09-02 |  | 2 | 2
27 | Implement"Edit News" function | 2017-10-01 | 2017-11-01 |  | 15 | 17
28 | Team Meeting | 2017-06-02 | 2017-06-02 | MinhDoan | 2 | 2
29 | Mentor Meeting | 2017-06-02 | 2017-06-02 |  | 2 | 4
30 | Training Technical | 2017-07-02 | 2017-07-02 |  | 2 | 2
31 | Implement "Show Detail Account" function | 2017-07-02 | 2017-08-02 |  | 14 | 15
32 | Demo "Login" function | 2017-09-02 | 2017-09-02 |  | 2 | 1
33 | Demo "Create Account" function | 2017-09-02 | 2017-09-02 |  | 1 | 1
34 | Demo " Show Account" function | 2017-09-02 | 2017-09-02 |  | 1 | 1
35 | Demo "Edit Account" function | 2017-09-02 | 2017-09-02 |  | 2 | 2
36 | Team Meeting | 2017-06-02 | 2017-06-02 | TaiNguyen | 2 | 2
37 | Mentor Meeting | 2017-06-02 | 2017-06-02 |  | 2 | 4
38 | Training Technical | 2017-07-02 | 2017-07-02 |  | 2 | 2
39 | Implement "Activate Account" function | 2017-07-02 | 2017-08-02 |  | 17 | 16
40 | Demo "Login" function | 2017-09-02 | 2017-09-02 |  | 2 | 1
41 | Demo "Create Account" function | 2017-09-02 | 2017-09-02 |  | 1 | 1
42 | Demo " Show Account" function | 2017-09-02 | 2017-09-02 |  | 1 | 1
43 | Demo "Edit Account" function | 2017-09-02 | 2017-09-02 |  | 2 | 2
44 | Implement "Transfer News" function | 2017-10-01 | 2017-11-01 |  | 18 | 20
45 | Mentor Meeting | 2017-06-02 | 2017-06-02 | XuanThaiHien | 2 | 4
46 | Training Technical | 2017-07-02 | 2017-07-02 |  | 2 | 2
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 43 | 44
|  |  |  | HienNguyen | 42 | 43
|  |  |  | KhoiNguyen | 37 | 42
|  |  |  | MinhDoan | 26 | 28
|  |  |  | TaiNguyen | 47 | 49
|  |  |  | XuanThaiHien | 4 | 6

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time