## Report
WEEKLY REPORT
WEEK: 21
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Implement "View News" function on server | 20/2/2017 | 22/2/2017 | HaiTran | 14 | 16
2 | Implement "View News" function on frontend for user | 20/2/2017 | 22/2/2017 |  | 20 | 18
3 | Training Technical | 23/2/2017 | 23/2/2017 |  | 2 | 2
4 | Implement "Transfer News" function on frontend | 23/2/2017 | 24/2/2017 |  | 6 | 6
5 | Implement "Edit News"function on frontend | 23/2/2017 | 24/2/2017 |  | 4 | 5
6 | Mentor Meeting | 24/2/2017 | 24/2/2017 |  | 2 | 3
7 | Presentation EOMP2 | 25/2/2017 | 25/2/2017 |  | 2 | 2
8 | Team Meeting | 25/2/2017 | 25/2/2017 |  | 1 | 1
9 | Implement "View News" function on server | 20/2/2017 | 22/2/2017 | HienNguyen | 16 | 16
10 | Training Technical | 23/2/2017 | 23/2/2017 |  | 2 | 2
11 | Implement "Transfer News" function on server | 23/2/2017 | 24/2/2017 |  | 6 | 7
12 | Implement "Edit News" function on server | 23/2/2017 | 24/2/2017 |  | 10 | 11
13 | Mentor Meeting | 24/2/2017 | 24/2/2017 |  | 2 | 3
14 | Presentation EOMP2 | 25/2/2017 | 25/2/2017 |  | 2 | 2
15 | Team Meeting | 25/2/2017 | 25/2/2017 |  | 1 | 1
16 | Training Technical | 23/2/2017 | 23/2/2017 | KhoiNguyen | 2 | 2
17 | Implement "Edit News" function on server | 23/2/2017 | 24/2/2017 |  | 5 | 7
18 | Mentor Meeting | 24/2/2017 | 24/2/2017 |  | 2 | 3
19 | Presentation EOMP2 | 25/2/2017 | 25/2/2017 |  | 2 | 2
20 | Team Meeting | 25/2/2017 | 25/2/2017 |  | 1 | 1
21 | Implement "Create draft" function on frontend | 20/2/2017 | 22/2/2017 | MinhDoan | 14 | 14
22 | Training Technical | 23/2/2017 | 23/2/2017 |  | 2 | 2
23 | Import data into database for function "Manage News" | 23/2/2017 | 24/2/2017 |  | 3 | 4
24 | Mentor Meeting | 24/2/2017 | 24/2/2017 |  | 2 | 3
25 | Presentation EOMP2 | 25/2/2017 | 25/2/2017 |  | 2 | 2
26 | Team Meeting | 25/2/2017 | 25/2/2017 |  | 1 | 1
27 | Implement "View News" function on frontend for admin | 20/2/2017 | 22/2/2017 | TaiNguyen | 18 | 15
28 | Training Technical | 23/2/2017 | 23/2/2017 |  | 2 | 2
29 | Implement "Transfer News" function on frontend | 23/2/2017 | 24/2/2017 |  | 8 | 7
30 | Implement "Edit News"function on frontend | 23/2/2017 | 24/2/2017 |  | 6 | 6
31 | Mentor Meeting | 24/2/2017 | 24/2/2017 |  | 2 | 3
32 | Presentation EOMP2 | 25/2/2017 | 25/2/2017 |  | 2 | 2
33 | Team Meeting | 25/2/2017 | 25/2/2017 |  | 1 | 1
34 | Mentor Meeting | 24/2/2017 | 24/2/2017 | XuanThaiHien | 2 | 3
35 | Presentation EOMP2 | 25/2/2017 | 25/2/2017 |  | 2 | 2
36 | Team Meeting | 25/2/2017 | 25/2/2017 |  | 1 | 1
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 51 | 53
|  |  |  | HienNguyen | 39 | 42
|  |  |  | KhoiNguyen | 12 | 15
|  |  |  | MinhDoan | 24 | 26
|  |  |  | TaiNguyen | 39 | 36
|  |  |  | XuanThaiHien | 5 | 6

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time