## Sheet1
EFFORT LOG
WEEK: 23
No. | Task | From | To | Estimate Time | Actual Time
1 | Team Meeting | 2017-06-03 | 2017-06-03 | 2 | 2
2 | Implement "Add categories" function on frontend | 2017-06-03 | 2017-07-03 | 10 | 12
3 | Training Technical | 2017-07-03 | 2017-07-03 | 2 | 2
4 | Implement "Edit categories" function on frontend | 2017-07-03 | 2017-09-03 | 17 | 19
5 | Mentor Meeting | 2017-10-03 | 2017-10-03 | 2 | 3
6 | Implement "Delete categories" function on frontend | 2017-10-03 | 2017-11-03 | 6 | 6
7 | Implement "Create Banner" function on frontend | 2017-10-03 | 2017-11-03 | 18 | 18