## Report
WEEKLY REPORT
WEEK: 23
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 2017-06-03 | 2017-06-03 | HaiTran | 2 | 2
2 | Implement "Add categories" function on server | 2017-06-03 | 2017-07-03 |  | 12 | 14
3 | Training Technical | 2017-07-03 | 2017-07-03 |  | 2 | 2
4 | Implement "Edit categories" function on server | 2017-07-03 | 2017-09-03 |  | 18 | 14
5 | Mentor Meeting | 2017-10-03 | 2017-10-03 |  | 2 | 3
6 | Implement "Delete categories" function on server | 2017-10-03 | 2017-11-03 |  | 5 | 5
7 | Implement "Create Banner" function on server | 2017-10-03 | 2017-11-03 |  | 14 | 12
8 | Implement "Create Banner" function on frontend | 2017-10-03 | 2017-11-03 |  | 16 | 18
9 | Team Meeting | 2017-06-03 | 2017-06-03 | HienNguyen | 2 | 2
10 | Implement "Add categories" function on server | 2017-06-03 | 2017-07-03 |  | 15 | 16
11 | Training Technical | 2017-07-03 | 2017-07-03 |  | 2 | 2
12 | Implement "Edit categories" function on server | 2017-07-03 | 2017-09-03 |  | 20 | 22
13 | Mentor Meeting | 2017-10-03 | 2017-10-03 |  | 2 | 3
14 | Implement "Delete categories" function on server | 2017-10-03 | 2017-11-03 |  | 8 | 6
15 | Implement "Create Banner" function on server | 2017-10-03 | 2017-11-03 |  | 18 | 17
16 | Team Meeting | 2017-06-03 | 2017-06-03 | KhoiNguyen | 2 | 2
17 | Implement "Add categories" function on frontend | 2017-06-03 | 2017-07-03 |  | 8 | 6
18 | Training Technical | 2017-07-03 | 2017-07-03 |  | 2 | 2
19 | Mentor Meeting | 2017-10-03 | 2017-10-03 |  | 2 | 3
20 | Team Meeting | 2017-06-03 | 2017-06-03 | MinhDoan | 2 | 2
21 | Implement frontend News on ionic 2 | 2017-06-03 | 2017-08-03 |  | 20
22 | Training Technical | 2017-07-03 | 2017-07-03 |  | 2 | 2
23 | Implement "Edit categories" function on frontend | 2017-07-03 | 2017-09-03 |  | 15 | 16
24 | Mentor Meeting | 2017-10-03 | 2017-10-03 |  | 2 | 3
25 | Team Meeting | 2017-06-03 | 2017-06-03 | TaiNguyen | 2 | 2
26 | Implement "Add categories" function on frontend | 2017-06-03 | 2017-07-03 |  | 10 | 12
27 | Training Technical | 2017-07-03 | 2017-07-03 |  | 2 | 2
28 | Implement "Edit categories" function on frontend | 2017-07-03 | 2017-09-03 |  | 17 | 19
29 | Mentor Meeting | 2017-10-03 | 2017-10-03 |  | 2 | 3
30 | Implement "Delete categories" function on frontend | 2017-10-03 | 2017-11-03 |  | 6 | 6
31 | Implement "Create Banner" function on frontend | 2017-10-03 | 2017-11-03 |  | 18 | 18
32 | Implement frontend News on ionic 2 | 2017-06-03 | 2017-08-03 | XuanThaiHien | 20
33 | Mentor Meeting | 2017-10-03 | 2017-10-03 |  | 2 | 3
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 71 | 70
|  |  |  | HienNguyen | 67 | 68
|  |  |  | KhoiNguyen | 14 | 13
|  |  |  | MinhDoan | 41 | 23
|  |  |  | TaiNguyen | 57 | 62
|  |  |  | XuanThaiHien | 22 | 3

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time