## Sheet1
EFFORT LOG
WEEK: 3
No. | Task | From | To | Estimate Time | Actual Time
1 | Mentor Meeting | 17/10/2016 | 17/10/2016 | 2 | 5
2 | Team Meeting | 18/10/2016 | 18/10/2016 | 2 | 2
3 | Define risk management plan template | 19/10/2016 | 20/10/2016 | 3 | 4
4 | Review Requirement Management Plan Template | 20/10/2016 | 21/10/2016 | 3 | 3