## Report
WEEKLY REPORT
WEEK: 5
No. | Task | From | To | Assign to | Estimate Time | Actual Time
1 | Team Meeting | 31/10/2016 | 31/10/2016 | HaiTran | 3 | 3
2 | Review Requirement Plan | 2016-01-11 | 2016-01-11 |  | 3 | 2
3 | Review Implement Plan | 2016-01-11 | 2016-01-11 |  | 2 | 1
4 | Review Architecture and Design Plan | 2016-01-11 | 2016-01-11 |  | 5 | 7
5 | Update Requirement Plan | 2016-02-11 | 2016-02-11 |  | 4 | 5
6 | Update Architecture and Design Plan | 2016-02-11 | 2016-02-11 |  | 4 | 6
7 | Develop Estimation | 2016-03-11 | 2016-04-11 |  | 6 | 8
8 | Review Software Development Process | 2016-04-11 | 2016-05-11 |  | 4 | 4
9 | Review Schedule | 2016-04-11 | 2016-05-11 |  | 3 | 2
10 | Review Training Plan | 2016-04-11 | 2016-05-11 |  | 2 | 2
11 | Team Meeting | 31/10/2016 | 31/10/2016 | HienNguyen | 2 | 3
12 | Review Requirement Plan | 2016-01-11 | 2016-01-11 |  | 4 | 2
13 | Review Implement Plan | 2016-01-11 | 2016-01-11 |  | 1 | 1
14 | Review Architecture and Design Plan | 2016-01-11 | 2016-01-11 |  | 7 | 7
15 | Develop Schedule | 2016-03-11 | 2016-05-11 |  | 8 | 6
16 | Develop Master Plan | 2016-03-11 | 2016-04-11 |  | 2 | 3
17 | Review Configuration Plan | 2016-04-11 | 2016-05-11 |  | 3 | 5
18 | Review Software Development Process | 2016-04-11 | 2016-05-11 |  | 3 | 4
19 | Review Schedule | 2016-04-11 | 2016-05-11 |  | 1 | 2
20 | Review Training Plan | 2016-04-11 | 2016-05-11 |  | 1 | 2
21 | Team Meeting | 31/10/2016 | 31/10/2016 | KhoiNguyen | 2 | 3
22 | Review Requirement Plan | 2016-01-11 | 2016-01-11 |  | 3 | 2
23 | Review Implement Plan | 2016-01-11 | 2016-01-11 |  | 1 | 1
24 | Review Architecture and Design Plan | 2016-01-11 | 2016-01-11 |  | 5 | 7
25 | Update Implement Plan | 2016-02-11 | 2016-02-11 |  | 3 | 2
26 | Develop Configuration Plan | 2016-03-11 | 2016-05-11 |  | 8 | 11
27 | Review Software Development Process | 2016-04-11 | 2016-05-11 |  | 5 | 4
28 | Review Schedule | 2016-04-11 | 2016-05-11 |  | 2 | 2
29 | Review Training Plan | 2016-04-11 | 2016-05-11 |  | 1 | 2
30 | Team Meeting | 31/10/2016 | 31/10/2016 | MinhDoan | 1 | 3
31 | Review Requirement Plan | 2016-01-11 | 2016-01-11 |  | 4 | 2
32 | Review Implement Plan | 2016-01-11 | 2016-01-11 |  | 2 | 1
33 | Review Architecture and Design Plan | 2016-01-11 | 2016-01-11 |  | 5 | 7
34 | Gather Question List | 2016-03-11 | 2016-04-11 |  | 2 | 2
35 | Review Test Plan | 2016-04-11 | 2016-05-11 |  | 4 | 3
36 | Review Software Development Process | 2016-04-11 | 2016-05-11 |  | 3 | 4
37 | Review Schedule | 2016-04-11 | 2016-05-11 |  | 1 | 2
38 | Review Training Plan | 2016-04-11 | 2016-05-11 |  | 1 | 2
39 | Team Meeting | 31/10/2016 | 31/10/2016 | TaiNguyen | 3 | 3
40 | Review Requirement Plan | 2016-01-11 | 2016-01-11 |  | 5 | 2
41 | Review Implement Plan | 2016-01-11 | 2016-01-11 |  | 2 | 1
42 | Review Architecture and Design Plan | 2016-01-11 | 2016-01-11 |  | 6 | 7
43 | Develop Software Development Process | 2016-03-11 | 2016-05-11 |  | 6 | 9
44 | Develop Training Plan | 2016-03-11 | 2016-05-11 |  | 3 | 4
45 | Review Software Development Process | 2016-04-11 | 2016-05-11 |  | 4 | 4
46 | Review Schedule | 2016-04-11 | 2016-05-11 |  | 2 | 2
47 | Review Training Plan | 2016-04-11 | 2016-05-11 |  | 1 | 2
48 | Team Meeting | 31/10/2016 | 31/10/2016 | XuanThaiHien | 2 | 3
49 | Review Requirement Plan | 2016-01-11 | 2016-01-11 |  | 5 | 2
50 | Review Implement Plan | 2016-01-11 | 2016-01-11 |  | 2 | 1
51 | Review Architecture and Design Plan | 2016-01-11 | 2016-01-11 |  | 6 | 7
52 | Develop Test Plan | 2016-03-11 | 2016-05-11 |  | 9 | 12
53 | Review Software Development Process | 2016-04-11 | 2016-05-11 |  | 3 | 4
54 | Review Schedule | 2016-04-11 | 2016-05-11 |  | 1 | 2
55 | Review Training Plan | 2016-04-11 | 2016-05-11 |  | 2 | 2
[5 empty] | ESTIMATE | ACTUAL
|  | Total |  | HaiTran | 36 | 40
|  |  |  | HienNguyen | 32 | 35
|  |  |  | KhoiNguyen | 30 | 34
|  |  |  | MinhDoan | 23 | 26
|  |  |  | TaiNguyen | 32 | 34
|  |  |  | XuanThaiHien | 30 | 33

## HaiTran
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## HienNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## KhoiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## TaiNguyen
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## MinhDoan
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time

## XuanThaiHien
EFFORT LOG
WEEK:
No. | Task | From | To | Estimate Time | Actual Time